## Slide 1: CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
University of Benin, Edo state, Nigeria
ACE AWP Annex 2019

## Slide 2: Content
Update Slide on implementation (results/fund utilization)
Key Goals for ACE for Jan 2019-March 2020
Action plan/priorities for DLIs not achieved
  Revenue generation
  Increase number of regional students
  International accreditation

## Slide 3: Update Slide on implementation
CERHI has achieved all her DLRs except for international accreditation and revenue generation as shown below

## Slide 4: Disbursement Linked Indicators
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date | Comments
DLI #1: Regional specialization endorsed and institutional readiness | The national representative in the Steering Committee has endorsed a resolution to promote regional specialization among participating Universities Conditions for Effectiveness have been met | Achieved | 

## Slide 5: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.1: New short term students in ACE courses of which 30% must be regional students (97 regional) | CERHI has achieved her 4 year target as at April 2018 with (507 regional students reached) | 

## Slide 6: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.2: New Master students in ACE courses of which 30% must be regional students Regional Masters – 7 | 11 students are currently on CERHI program | 7 Students from Ghana and 4 students from Guinea are currently on the 2017/2018 Masters programme and 24 students from Ghana, Malawi, Guinea and Cameroon have been enrolled on the 2018/2019 session

## Slide 7: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.3: New PhD students in ACE courses of which 30% must be regional students Regional PhD- 5 DLI#2.4: No of outreach “periods” for faculty, master and PhD students 90 Students 10 Faculty | 5 (100%) 64 (71%) students | 4 Students from Ghana and 1 students from Cameroon have been admitted into the 2017/2018 PhD programme. And 6 regional students have been enrolled for 2018/2019 session 3rd set of students will be eligible for outreach in January 2019.

## Slide 8: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.5: Certification and evaluation of quality of education programs (2 programmes) | Agency for Public Health Education on Accreditation (APHEA) (50%) National Universities Commission | At institutional accreditation stage . Submitted self evaluation as at December 2018 Have achieved accreditation for the 9 courses.

## Slide 9: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.6 Published articles in internationally recognized and peer reviewed journals (8 publications) DLI#2.7: Externally revenue generation (100,000) | 96 (1,200%) $185,497.38 | This DLI has consistently been over achieved. CERHI’s has achieved her 2018 target for this DLI.

## Slide 10: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.8: Meeting milestones for improved learning and research environment specified in the Performance and Funding contracts | 2.8.1- Begin building CERHI center complex structure and upgrading of classroom by installation of modern classroom furniture and facilities 2.8.2- Completion of building for CERHI center, purchase and installation of furniture in the CERHI complex with e-learning platform, video conferencing and furnishing for offices, seminar rooms and library | Completed (100%) and verified as at April, 2018 Completed (100%) and verified as at April, 2018

## Slide 11: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI #2: Excellence in education and research capacity and development impact | DLI#2.8: Meeting milestones for improved learning and research environment specified in the Performance and Funding contracts | 2.8.3- Purchase and installation of CERHI complex generator and laboratory equipment 2.8.4- 100% completion of renovation of International student hostel and faculty guest house and purchase and installation of furniture and generator for the International student hostel and faculty guest house to meet international standards. | Completed (100%) and verified as at April, 2018 Completed (100%) and verified as at Sept., 2018

## Slide 12: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI#3 Timely, transparent financial management | DLI#3.1: Timely withdrawal application DLI#3.2: Functioning audit committee under the university Council | Achieved and verified as at Sept., 2018 Achieved and verified as at Sept., 2018 | 

## Slide 13: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI#3 Timely, transparent financial management | DLI#3.3: Functioning Univ. internal audit unit DLI#3.4:Web transparency on financial management | Achieved and verified as at Sept., 2018 Achieved and verified as at Sept., 2018 | 

## Slide 14: Disbursement Linked Indicators…
Disbursement Linked Indicator | Action to be Completed (2018 TARGET) | Achieved to date (2018) | Comments
DLI#4 Timely and audited Procurement | DLI# 4.1 Timely procurement audit DLI#4.2: Timely and Satisfactory Procurement Progress | Achieved Funds on this DLI has been reallocated to other DLIs | 

## Slide 15: CERHI FUNDS UTILIZATION
S/N | DESCRIPTION | CERHI RECORDS AS AT NOVEMBER 2018 (N)
1 | Total Grant (SDR 5,100,000) | 2,221,138,806.30
2 | Total IDA funds received to date (Nov. 2018) | 1,002,970,499.10
3 | IDA funds received Jan 1- Nov 30 2018 | 204,563,975.69
4 | Total IDA funds used to date | 960,047,831.28
5 | IDA funds used Jan 1- Nov 30, 2018 | 368,194,393.28
6 | Total IDA funds used to date / Total grant (%) | 43.22
7 | IDA funds used Jan 1- Nov 30, 2018/ Total grant (%) | 16.58
8 | Total IDA funds used to date/ Total IDA funds received to date (%) | 95.72

## Slide 16: Key goals for 2019
International accreditation
Increase number of outreach period (internship)
Increase by 50% the number of regional students for short term courses
Increase by 50% the number of regional students for masters program
Increase by 50% the number of regional students for PhD program
To be more visible within and around the university as a research and medical centre

## Slide 17: Action plan/priorities for DLIs not achieved
  International accreditation
  Whilst following up on APHEA on the institutional accreditation, we are also applying to HCERES for program accreditation
  Revenue generation
  CERHI is seeking funds through proposal writing and is also generating funds from students’ school fees, renting of halls, bus, hostel, guest house.
  Increase number of regional students
  Visits and adverts in other countries during short courses and other meetings
  Action Plan to accelerate fund utilization
  CERHI plans to utilize gained funds on sustainable activities and strengthening her systems as can be seen in the 2019 workplan

## Slide 18: Action Plan to accelerate fund utilization
Plan for disbursement based on results and verification
CERHI is up to date on her report submission and verification of 2018 results are on going.
CERHI will be submitting quarterly results of 2019 activities
Plan for full fund utilization by close of project
CERHI plans on completing all activities by November 2019 so as to have a-zero account by March 2020

## Slide 19: Major Challenges?
Delays in achieving international accreditation (APHEA has taken almost 2 years)