## WORKS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦306 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN,NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2019– December, 2019
WORKS
2. | Prior Review Threshold:
| Procurement Method | Threshold for use of Method (US$) | Prior review Threshold (US$) | Comments
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
Actual
| Total Cost |  | 0

## GOODS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦305 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2019– December, 2019
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR | REMARKS
RESEARCH/LABORATORY EQUIPMENT
| 2 Manikins with simulators | WB | 200000 | National Competitive bidding | Post- Qualification | N/A | Post Review | 9th-Jan-19 | 7th-Feb-19 | Plan | N/A | N/A | 8th-march-19 | 9th-April-19 | 2019-05-17 | N/A | 200000 | 11th-June-19 | 11th-June-19 | 18th-June-19 | 18th-Sept-19
Actual
LABORATORY SUPPLIES
| Procurement of laboratory supplies and consumables | WB | 40000 | Shopping | Post- Qualification | N/A | Post Review | 9th-Jan-19 | 7th-Feb-19 | Plan | N/A | N/A | 8th-march-19 | 9th-April-19 | 2019-05-17 | N/A | 100000 | 11th-June-19 | 11th-June-19 | 18th-June-19 | 18th-Sept-19
Actual
STATIONERY, LECTURE MATERIALS
| Procurement of Orientation Handbook,Stationeries and Lecture Materials. | WB | 10000 | Shopping | Post- Qualification | N/A | Post Review | 9th-Jan-19 | 7th-Feb-19 | Plan | N/A | N/A | 8th-march-19 | 9th-April-19 | 2019-05-17 | N/A | 10000 | 11th-June-19 | 11th-June-19 | 18th-June-19 | 18th-July-19
Actual
PROCUREMENT OF SUV
| Procurement of a Sport Utility Vehicle (SUV) with registration. | WB | 50000 | Shopping | Post- Qualification | N/A | Post Review | 9th-Jan-19 | 7th-Feb-19 | Plan | N/A | N/A | 8th-march-19 | 9th-April-19 | 2019-05-17 | N/A | 50000 | 11th-June-19 | 11th-June-19 | 18th-June-19 | 18th-Sept-19
Actual
| TOTAL |  | 300000

## CONSULTANCY SERVICES
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦306 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2019– December, 2019
CONSULTANCY SERVICES
2. | Prior Review Threshold:
Consultants (see Note 3)
|  |  | Threshold | Prior review
| Procurement Method |  | for use of Method | Threshold | Nature of Goods
|  |  | (US$) | (US$)
| 1. Quality and Cost Based Selection (QCBS) |  | N/A | N/A
| 2. Consultants Qualification Selection (CQS) |  | N/A | N/A
| 3. Least Cost Selection (LCS) |  | N/A | N/A
| 4. Fixed Budget Selection (FBS) |  | N/A | N/A
| 5. Selection of Individual Consultants (SIC) |  | N/A | N/A
| 6. Single Source Selection (SSS) |  | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule | [8 empty] | Request for Expression of Interest |  |  |  |  | Request for Proposal & Short List |  | Proposals |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Assignment | Source of Funds | Estimated Amount (US$) | Selection Method | Prior/Post Review | Lumpsum or Timed-Based | Plan vs. Actual | Submission Date | No-objection Date | Date Published | Submission Date | Plan vs. Actual | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) & (F) | Submission Negotiations Report | No-objection Award & Negotiations | Plan vs. Actual | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Consultancy services of National and International guest lecturers to visit CERHI for collaborative research and grants proposal development | WB | 12000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-18 | 12th-Dec-19 | NA | NA | NA | NA | NA
Actual
| Cost of HCERES Accreditation for 3 CERHI courses | WB | 150000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-18 | 12th-Dec-19 | NA | NA | NA | NA | NA
Actual
| Total Cost |  | 162000
Note
|  | Please note that the yellow cells do not require dates, as the project would not be required to send to the WB for Clearance. | [6 empty] | Project should replace the dates with Not Applicable " NA".
1
2

## Simplified P plan (hidden)
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017–December, 2017
OPERATING COST
2. | Prior Review Threshold:
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A | N/A
| 2. NCB (Goods) | N/A | N/A | N/A
| 1. ICB (Works) | N/A | N/A | N/A
| 4. NCB (Works) | N/A | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A | N/A
| 6. Shopping | N/A | N/A | N/A
| 7. Direct Contracting | N/A | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [6 empty] | DISBURSEMENT LINKED INDICATORS
| Description of Expenses | Source of Funds | Estimated Amount (US$) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter | Total Amount (US$) | Plan Vs Actual | DLI/DLR
| Audit expenses (Procurement and Account audit) | WB | 17500 | 3000 | 4000 | 3000 | 7500 | 17500 | Plan
Actual
| Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | WB | 30000 | 6000 | 7500 | 10500 | 6000 | 30000 | Plan
Actual
| Student recruitment (Advertisements, portal, travels, interview and printing) | WB | 13500 | 3000 |  | 7000 | 3500 | 13500 | Plan
Actual
| Scaling up PhD Programmes (increasing students numbers,visiting and professors and researchers) Honoraria of non employed staff) | WB | 36000 | 6000 | 9000 | 13500 | 7500 | 36000 | Plan
Actual
| International Research Collabration and Joint Research Programme among students faculties | WB | 60000 | 11000 | 15000 | 22500 | 11500 | 60000 | Plan
Actual
| Local Travels | WB | 24000 | 5000 | 6000 | 9000 | 4000 | 24000 | Plan
Actual
| Faculty Developments :capacity building in curricala and non based programmes | WB | 50000 | 9000 | 12500 | 19000 | 9500 | 50000 | Plan
Actual
| Research grant pools (to small and medium scale applied research) | WB | 225000 | 5000 | 5000 | 8500 | 4500 | 225000 | Plan
Actual
| Publication in high impact factor journals by faculty and students (cost of publication) | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | WB | 10500 | 2000 | 2500 | 4000 | 2000 | 10500 | Plan
Actual
| Provide equitable distribution of excellent high quality open and distant learning | WB | 35000 | 6000 | 8750 | 13500 | 6750 | 35000 | Plan
Actual
| Provide equitable distrbution of excellence and high quality research by instituting doctoral research | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| provide broad-based scientific capacity of students through intenships, short courses and SIWES | WB | 40000 | 7000 | 10000 | 15000 | 8000 | 40000 | Plan
Actual
| Provision of extension and community mobilization services/awareness | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Ensure social relevance through annual regional stakeholders meeting in participating countries NRCRI | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
| Engagement in joint research project among participating institutions | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Introdution of regional working groups for research groups | WB | 16000 | 3000 | 6000 | 4000 | 3000 | 16000 | Plan
Actual
| Short term exchange programmes within Nigeria | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Schorlaships research for Cefter Students and | WB | 150000 | 30000 | 35000 | 55000 | 30000 | 150000 | Plan
Actual
| Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Research grant pools to support faculty and student's international applied research on post-harvest losses | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Workshop at AOCAY partner. | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Development joint curricula among partnership institution and CEFTER departments | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Identification of joint training needs for academic and professional staff in post-harvest science and management | WB | 12000 | 2000 | 3000 | 4500 | 2500 | 12000 | Plan
Actual
| Stakeholders meeting to review progress at ACE | WB | 12000 | 2000 | 3000 | 5000 | 2000 | 12000 | Plan
Actual
| Domestication of curricula in the departments at BSU (Independent review of draft curricula) | WB | 6000 | 1000 | 1500 | 2000 | 1500 | 6000 | Plan
Actual
| Faculty and students training (Staff on PG fellowship) | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | WB | 15000 | 3500 | 4000 | 4500 | 3000 | 15000 | Plan
Actual
| Institute lecture series: NSPRI organised on Impact of Climate change on PHL | WB | 10000 | 2500 | 2500 | 3000 | 2000 | 10000 | Plan
Actual
| Produce and circulate monographs targeted at awareness creation and extension to rural farmers | WB | 6000 | 1000 | 2000 | 2500 | 500 | 6000 | Plan
Actual
| Support Research fellowships( Sponsor staff of partner institutions on PG programs) | WB | 15000 | 3500 | 3500 | 6000 | 2000 | 15000 | Plan
Actual
| Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | WB | 35000 | 6000 | 6000 | 15000 | 8000 | 35000 | Plan
Actual
| Start long faculty exchanges between CEFTER, and Universities in Africa | WB | 24000 | 5000 | 6000 | 10000 | 3000 | 24000 | Plan
Actual
| Start of joint research projects between CEFTER,universties and research insttutes elsewhere in Africa | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
Actual
| Produce operational manuals for students | WB | 6000 |  |  | 3000 | 3000 | 6000 | Plan
Actual
| Monitoring and evaluation (Travels, stationaries) | WB | 18000 | 4000 | 4500 | 7000 | 2500 | 18000 | Plan
Actual
| Fund raising activities (Meetings, travels, media) | WB | 10500 | 3000 | 2500 | 4500 | 1500 | 10500 | Plan
Actual
| NgREN Communication Services | WB | 300000 | 60000 | 50000 | 130000 | 60000 | 300000 | Plan
Actual
| Casual staff on Utility services (Cleaners, security) | WB | 40000 | 8000 | 10000 | 14000 | 8000 | 40000 | Plan
Actual
| Provide Automated accounting System | WB | 20000 | 4500 | 6000 | 6500 | 3000 | 20000 | Plan
Actual
|  | TOTAL | 1429000 | 238000 | 275750 | 480500 | 240250 | 1429000
NOTE:
1. operating manuals for students are produced every year.

## Operating Cost
SUB-COMPONENT | ACTIVITIES
Component 1: Strengthening Africa Centers of Excellence
Activity No | ACIVITIES | ESTIMATED BUDGET ($)
Component 1: Strengthening Africa Centers of Excellence
1 | Support students and faculty with outreach to civil society organizations | 40000
2 | Support for regional and international conference attendance and manuscript preparation by students and faculty | 150000
3 | Visit to regional countries and partner institutions to attract foreign students and support short courses | 50000
4 | Office running costs | 47536.64
5 | Quarterly Expanded Project Management Committee (EPMC) Meeting . | 40000
6 | Research workshop | 10000
7 | Support for 9 research teams to conduct researches on their various thematic areas | 260000
8 | Students Internship/Faculty Exchange | 130000
9 | Lectures and end of semester examination | 50000
10 | Support for work of the centre’s internal audit committee and annual external financial audit under the University’s Governing Council | 2000
11 | Conduct 18 short courses in CERHI and in national and regional partner institutions | 270000
12 | Support for CERHI staff to be part of short courses in partner institutions | 80000
13 | Maintenance of CERHI Faculty Guest house | 4000
14 | Maintenance of CERHI International students' hostel | 8000
15 | Annual renewal of Science Direct | 78431.37
16 | Annual renewal of EBSCOHOST | 26143.79
17 | Annual renewal of NGREN | 58823.53
18 | Research repository data | 32679.74
19 | Management Retreat for PMC Members. | 15000
20 | International Advisory Board Meeting (IAB) | 30000
21 | Weekly Project Management Committee meeting | 10000
22 | Running of CERHI business centre | 1000
23 | Trainings and workshops for faculty, staff and students | 270000
24 | Salaries for project staff | 71000
25 | Working with regional and international partners on staff and student exchange programs and researches | 290000
26 | Meetings and activities related to fund-raising and proposal development | 40000
27 | Servicing and maintenance of laboratory equipments | 30000
28 | Training and re-training of laboratory staff | 30000
2124615.07

## SUMMARY
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
| UNIVERSITY OF BENIN, EDO STATE | 2019 procurement plan
SUMMARY
THE EXCHANGED RATE USED IS ₦306 PER US DOLLAR
GOODS
| RESEARCH/LABORATORY EQUIPMENT | 200000
| LOT 2 : LABORATORY EQUIPMENT | 200287.71
| LABORATORY SUPPLIES | 40000
| STATIONERY, LECTURE MATERIALS | 10000
| PROCUREMENT OF SUV | 50000
TOTAL |  |  | 300000
WORKS |  |  | 0
| CONSULTANCY SERVICES |  | 162000
OPERATING COST |  |  | 2124615.07
GRAND TOTAL |  |  | 2586615.07