## Sources and Uses of funds
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION, UNIVERSITY OF BENIN
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Statement of Sources and Uses of Funds
for the Semi Annual Period ending June, 2018
Cummulative for
Sources of Fund | Semi Annual Period ending June 2018 | Financial Year End (Jan-June, 2018)
Opening Cash Balance
Government Funds
World Bank IDA Funds | 161930708.17 | 161930708.17
Student Fees Naira |  | 0
Student Fees USD (39187.66 usd @305.25 ngn to 1usd) | 11962033.215 | 11962033.215
Total | 173892741.385 | 173892741.385
Add Receipts
World Bank IDA Funds | 54000000 | 54000000
IGR | 303980 | 303980
Refund | 563975.69 | 563975.69
Student Fees | 21488900 | 21488900
short course fees |  | 0
Tender Fees |  | 0
Total Financing | 250249597.075 | 250249597.075
Less: ACE Expenditure as per Project Implementation Plan
Enhanced Capacity To Deliver Regional High Quality Training
| 33161552.38 | 33161552.38
Enhanced Capacity To Deliver Applied Research To Address Regional Development Challenges
| 102177324.23 | 102177324.23
Build/Use Industry/Sector Partnership To Impact Of Ace On Development And Increased Relevance Of Centre Education And Research
| 6710383 | 6710383
Build And Strengthen Regional And International Academic Partnership
| 82267927.38 | 82267927.38
Enhance Governance And Management Of Ace And The Participating University
| 2286225.09 | 2286225.09
Total Uses of Funds By Components | 226603412.08 | 226603412.08
Closing Balances
World Bank IDA Funds | -1598804.63 | -1598804.63
IGR USD(82702.66 usd @305.25 ngn to 1usd) | 25244986.965 | 25244986.965
Total Closing Cash Balance | 23646182.335 | 23646182.335
0

## Uses of Funds as per PIM
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION, UNIVERSITY OF BENIN.
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds by project activities
For the Semi Annual Period ending June, 2018.
(NAIRA)
Expenditure | Semi Annual Period ending 30/6/ 2018 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year End |  | Variance | Project | PAD
| Actual | Planned | Variance | Actual | Planned | Variance
Expenditure Classification 1 as per Project Implementation Plan
Administrative Salaries | 2900000 | 15000000 | 12100000 | 2900000 | 15000000 | 12100000 | Funds Unutilised
Junior Staff Salaries | [5 empty] | 0 | Funds Unutilised
Vehicle |  | 10000000 |  |  | 10000000 | 10000000 | Funds Unutilised
Website Development |  | 3000000 |  |  | 3000000 | 3000000 | Funds Unutilised
Laboratory and Teaching Equipment | 18933815.86 | 40000000 | 21066184.14 | 18933815.86 | 40000000 | 21066184.14 | Positive variance.Actual expenditure less than budgeted
Transport and Travelling | 4974554.52 | 7000000 | 2025445.48 | 4974554.52 | 7000000 | 2025445.48 | Positive variance.Actual expenditure less than budgeted
Fuel Charges (Diesel, Petrol) | 2009730 | 8000000 | 5990270 | 2009730 | 8000000 | 5990270 | Positive variance.Actual expenditure less than budgeted
Guest Feeding and other charges | 747500 | 6000000 | 5252500 | 747500 | 6000000 | 5252500 | Positive variance.Actual expenditure less than budgeted
Entertainment and Hospitality | 1541392 | 3000000 | 2143980 | 1541392 | 3000000 | 1458608 | Positive variance.Actual expenditure less than budgeted
Communication and Postage Charges | 856020 | 2700000 | 1843980 | 856020 | 2700000 | 1843980 | Positive variance.Actual expenditure less than budgeted
Professional Conferences/Workshop (Local) | 947240 | 15000000 | 14052760 | 947240 | 15000000 | 14052760 | Positive variance.Actual expenditure less than budgeted
Vehicle Maintenance | 251300 | 2000000 | 1748700 | 251300 | 2000000 | 1748700 | Positive variance.Actual expenditure less than budgeted
Vehicle License and Insurance | 0 |  |  | 0
Sub Total | 33161552.38 | 111700000 |  | 33161552.38 | 111700000
Expenditure Classification 2 as per Project Implementation Plan | 0
Books, Journals, World Health Magazines, Etc. | 51982555 | 80000000 | 28017445 | 51982555 | 80000000 | 28017445 | Positive variance.Actual expenditure less than budgeted
Computer and Office Equipment | 3190599.61 | 25000000 | 21809400.39 | 3190599.61 | 25000000 | 21809400.39 | Positive variance.Actual expenditure less than budgeted
Generator 100kva |  | 5000000 | 5000000 |  | 5000000 | 5000000 | Funds Unutilised
Civil Works ( CERHI Building Complex) | 13606787.95 | 15000000 | 1393212.05 | 13606787.95 | 15000000 | 1393212.05 | Positive variance.Actual expenditure less than budgeted
Civil Works ( Renovation of Hostel and Guest House) |  | 50000000 | 50000000 |  | 50000000 | 50000000 | Funds Unutilised
Printing andStationeries | 624300 | 5000000 | 4375700 | 624300 | 5000000 | 4375700 | Positive variance.Actual expenditure less than budgeted
Consumables | 2138520 | 2500000 | 361480 | 2138520 | 2500000 | 361480 | Positive variance.Actual expenditure less than budgeted
Professional Associations and Journal Subscription fees | 778741.2 | 6500000 | 5721258.8 | 778741.2 | 6500000 | 5721258.8 | Positive variance.Actual expenditure less than budgeted
NHIS Charges for Students and CERHI Staff. |  | 1000000 | 1000000 |  | 1000000 | 1000000 | Funds Unutilised
Internet Subscription and IT Maintenance/Support | 4535600 | 45000000 | 40464400 | 4535600 | 45000000 | 40464400 | Positive variance.Actual expenditure less than budgeted
Laboratory Practice and Consumables |  | 3000000 | 3000000 |  | 3000000 | 3000000 | Funds Unutilised
Advert and Interviews Expenses | 50000 | 5000000 | 4950000 | 50000 | 5000000 | 4950000 | Positive variance.Actual expenditure less than budgeted
Professional Conferences /Workshop (Overseas) | 22578838.47 | 50000000 | 27421161.53 | 22578838.47 | 50000000 | 27421161.53 | Positive variance.Actual expenditure less than budgeted
Miscelaneous and Sundry Expenses | 2691382 | 5000000 | 2308618 | 2691382 | 5000000 | 2308618 | Positive variance.Actual expenditure less than budgeted
Sub Total | 102177324.23 | 298000000 |  | 102177324.23 | 298000000
Expenditure Classification 3 as per Project Implementation Plan | 0
Facility and infrastructure maintenance | 6665383 | 10000000 | 3334617 | 6665383 | 10000000 | 3334617 | Positive variance.Actual expenditure less than budgeted
Office equipment repairs | 45000 | 2000000 | 1955000 | 45000 | 2000000 | 1955000 | Positive variance.Actual expenditure less than budgeted
Sub Total | 6710383 | 12000000 |  | 6710383 | 12000000
Expenditure Classification 4 as per Project Implementation Plan | 0
Furniture & Fittings | 13672990.38 | 30000000 | 16327009.62 | 13672990.38 | 30000000 | 16327009.62 | Positive variance.Actual expenditure less than budgeted
Electrical Electronics Equipment | 21363257 | 20400000 | -963257 | 21363257 | 20400000 | -963257 | Negative variance.Actual expenditure more than budgeted
Curriculum Workshop | 26098160 | 40000000 | 13901840 | 26098160 | 40000000 | 13901840 | Positive variance.Actual expenditure less than budgeted
Students Scholarship/ Internship | 4060000 | 50000000 | 45940000 | 4060000 | 50000000 | 45940000 | Positive variance.Actual expenditure less than budgeted
Students Prizes and Awards |  | 3000000 | 3000000 |  | 3000000 | 3000000 | Funds Unutilised
Electricity Bill |  | 1000000 | 1000000 |  | 1000000 | 1000000 | Funds Unutilised
Water Rate/Bill and maintenance |  | 1000000 | 1000000 |  | 1000000 | 1000000 | Funds Unutilised
Teaching and Examination | 17073520 | 20000000 | 2926480 | 17073520 | 20000000 | 2926480 | Positive variance.Actual expenditure less than budgeted |  |  | .
Sub Total | 82267927.38 | 165400000 |  | 82267927.38 | 165400000
Expenditure Classification 5 as per Project Implementation Plan
Accounting Information System Software |  | 7000000 | 7000000 |  | 7000000 | 7000000 | Funds Unutilised
Staff Training | 1391400 | 30000000 | 28608600 | 1391400 | 30000000 | 28608600 | Positive variance.Actual expenditure less than budgeted
Bank Charges | 94825.09 |  | -94825.09 | 94827.75 |  | -94827.75 | Negative variance. No budget for this item.
Audit fees | 800000 | 1000000 | 200000 | 800000 | 1000000 | 200000 | Positive variance.Actual expenditure less than budgeted
Sub Total | 2286225.09 | 38000000 |  | 2286227.75 | 38000000
| 0 |  |  | 0
Grand Total Uses of Funds | 226603412.08 | 625100000 |  | 226603414.74 | 625100000
Work on the PAD/Life of project for the period
Grand total of the funds

## EEP Statement
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION, UNIVERSITY OF BENIN.
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the Period ending May 2018
|  | Cummulative for | Cummulative for
Eligible Expenditure Program (EEP) | Period ending May., 2018 (N) | Financial Year End (Jan-May 2018) (N) | PAD/Life of Project (Jul 2015-May 2018) (N)
EEP 1: Salaries | 1404194962.83 | 1404194962.83 | 10555539386.71
EEP 2: Non Procurable Expenditure as defined in Financing Agreement | 70209748.1415 | 70209748.1415 | 527776969.3355
Total EEPs | 1474404710.9715 | 1474404710.9715 | 11083316356.0455
Work on cummulative for the life of project for each Centre

## DLI Statement
CENTRE OF EXCELLENCE IN REPRODCUTIVE HEALTH INNOVATION, UNIVERSITY OF BENIN.
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
DLR 1.1 …Develop and manage CERHI Website | Plans are in progress to link website to partner institutions | Yes (70%) | $15,000 | nil | $15,000
DLR 1.2…Establish meeting schedules for the Project Implementation Committee and the International Advisory Board | PMC, EPMC and IAB meetings have been regular and well attended | Yes (100%) | $108,000 | nil | $108,000
DLR 1.3…Procure vehicles critical to centre transportation and organization | Yet to procure one car/SUV | Yes (50%) | $80,000 | nil | $80,000
DLR 1.4…Leadership identification and development of centre coordinators from the regional partner institutions | Co ordinators are regular at EPMC meetings. | Yes (100%) | $55,000 | nil | $55,000
DLR 2.1 …Organize curriculum review/development workshop involvement regional and international partners | Curriculum review/development from 25th March to 26th June 2015. Senate approval of courses on July 9th, 2015. | Yes (100%) | $68,500 | nil | $68,500
DLR 2.2…Develop new masters program curriculum | 4 new Masters in addition to a revision of the MPH curriculum was done | Yes (100%) | $24,000 | nil | $24,000
DLR 2.3…Enrol and run new masters programs | bb | Yes (100%) | $68,578 | nil | $68,578
Nursing 32
MPHRH 25
MPH 26
DLR 2.4…Develop new PhD curriculum | 4 new PhD curricula were developed | Yes (100%) | $19,000 | nil | $19,000
DLR 2.5…Enrol and run new PhD programs | Health economics 1 | Yes (100%) | $33,520 | nil | $33,520
O&G 2, Nursing 5
MPHRH 5
DLR 2.6 …Plan and execute short term courses in RH at UNIBEN and in partner institutions | Short course to be organized in Zaria. Funds have been released. Also short course on theses supervision/mentorship; and on systematic analysis planned for May 30 and May 31 respectively. | Yes (60%) | $157,740 | nil | $157,740
DLR 2.7 …Improving faculty teaching methods and faculty develop | Workshop on pedagogy organized by the University for all faculty. Also, workshop on e-library training organized by the University for faculty. | Yes (70%) | $40,000 | nil | $40,000
DLR 2.8 …Procurement of e-learning materials, new learning technologies, and multi-nodal learning materials and platforms | All departments have benefited from procurement of e learning materials. Access to online content, e-learning platform via NGREN has also been given to all HODs to share with faculty and students | Yes (80%) | $247,050 | nil | $247,050
DLR 2.9 …Design, initiate construction of teaching facility including seminar rooms and e-learning centre (combined with core research facility) | Civil work almost completed. Procurement process has begun for furniture, e-learning materials and equipment. | Yes (80%) | $400,000 | nil | $400,000
DLR 2.10 …Develop and deploy e-learning platform | All departments have interactive boards. Access to the online content, e-learning platform via the NGREN has been given to HODs to share with faculty and staff | Yes (100%) | $200,000 | nil | $200,000
DLR 3.1 …Procure General Research equipment. | Procurement process ongoing. Will be completed when the building is completely ready. | Yes (50%) | $169,159 | nil | $169,159
DLR 3.2…Build a multidisciplinary team to develop regional research collaborations | 8 research teams have been developed. Following a workshop on research agenda setting. Awaiting proposals from the team members. | Yes (60%) | $45,500 | nil | $45,500
DLR 3.3…Organize proposal writing, research methodology and publications workshop for students and faculty with outreach training in partner institutions. | Centre sponsored 14 faculty to workshop on master grant proposal writing and financial management in tertiary educational institutions | Yes (80%) | $112,000 | nil | $112,000
Workshop on research methodology was conducted for faculty and students
DLR 3.4…Support for regional and international conference attendance and manuscript preparation by students and faculty | The Centre has sponsored students/PMC members to workshops/international conferences | Yes (30%) | $35,000 | nil | $35,000
DLR 3.5…Design and establish core research facility (combined with teaching facility) | Awaiting completion of CERHI building | Spaces presently domiciled in participating departments | $400,000 | nil | $400,000
DLR 4.1 …Institutionalize regular exchange periods of students between regional partner institutions | A total of 135 students were scheduled for exchange. So far, the following internships have been funded and completed (22 Local, 61 National, 7 Regional, 4 International) | Yes (90%) | $26,000 | nil | $26,000
DLR 4.2…Faculty exchange programs between national and regional partners | Faculty exchange from NBS, Fed Univ Ekiti, UNN, Ghana, UI and Queens University ongoing | Yes (100%) | $80,000 | nil | $80,000
DLR 4.3…Outreaches to civil society organizations, development partners, the private sector and industry for short term outreach periods for placement of students in workplace experiences on RH. | Nursing students have completed outreach programme. Community Health students are presently undergoing outreach periods | Yes (100%) | $20,000 | nil | $20,000
DLR 4.4 …Support for setting up institutional accreditation arrangements with a regional and an international accreditation body | NUC has accredited 7 out of 9 programmes. Work in progress on international accreditation | Yes (50%) | $99,000 | nil | $99,000
DLR 4.5…Support for international students hostel and renovation of accommodation for visiting faculties from regional and international institutions | Management has approved a dedicated CERHI hostel and accommodation for visiting staff. Contract for renovation to upgrade this to an international hostel has been advertised. Tender to be opened May 2nd | Yes (40%) | $146,092 | nil | $146,092
DLR 5.1 …Support for work of the centre’s internal audit committee and annual financial audit under the University’s Governing Council | So far, 3 internal audit and 1 external audit has been carried out | Yes | $5,250 | nil | $5,250
Work on amount undisbursed