## CERHI
Name of Center | CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
Institution | UNIVERSITY OF BENIN |  |  | On Schedule
Country | NIGERIA
Center Leader | PROFESSOR FRIDAY OKONOFUA |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2021 - DECEMBER 2021
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Develop and support centre governance, structure and strategy \ DLI Action: 1
Sub-Action 1a: Meetingsand Partnerships
Activity 1: Bi-Weekly meetings of Project Management Committee Members | Once in 2 weeks meetings | Nil | [12 empty] | Bi-weekly meetings conducted | Nil | 2000 | 0 | 0 | Program Manager
Activity 2: Bi-Annual meeting of Industry and Sectoral Advisory Board members | Twice a year | All academic, industry and sectoral partners | [12 empty] | Bi-annual meet\ings conducted | Nil | 5000 | 0 | 0 | Project Coordinator
Activity 3: Annual meeting of International Advisory Board members | Once a year | All international academic partners | [12 empty] | Annual meeting conducted | Nil | 13000 | 0 | 0 | Centre Leader
Activity 4: Participate in 2 Regional ACE workshops by Project staff | Twice a year | All centres, experts and AAU and World Bank staff | [12 empty] | Project staff attend 2 ACE regional meetings | Nil | 60000 | 0 | 0 | Program Manager
Activity 5: Renew/ establish partnership and develop MOU with Partners | Continuous activity | All centre partners and new ones | [12 empty] | Patnerships renewed | Nil | 10000 | 0 | 15000 | Deputy Centre Leader
Sub-Action 1b: Internet and E-books and Journals subscription
Activity 1: Annual Subscription of NgREN | Payment for annual subscription | Nil | [12 empty] | NgREN subscibed | Nil | 20000 | 0 | 0 | Program Manager
Activity 2: Annual subscription of EBSCOHOST | Payment for annual subscription | Nil | [12 empty] | EBSCOHOST subscribed | Nil | 15000 | 0 | 0 | Program Manager
Activity 3: Annual subcription of Science-Direct | Payment for annual subscription | Nil | [12 empty] | Science-Direct subscribed | Nil | 15000 | 0 | 0 | Program Manager
Activity 4: Establish faculty-wide ICT-based Learning Management Systems (LMS) in collaborating faculty and College | Payment for annual subscription | Nil | [12 empty] | LMS installed | Nil | 80000 | 0 | 0 | Centre Leader
Sub-Action 1c: Payments
Activity 1: Stipends to regional students | Monthly stipends to for over 40 regional students (PhD and MSc) to cover feeding and other living expenses | Nil | [12 empty] | Stipends paid | Nil | 150000 | 0 | 0 | Accountant
Activity 2: Salaries for project staff | Monthly salaries for externally hired staff (Program Manager, Assistant Program Manager, Web Master/Communication Officer, M&E Assistants, Corp Members) | Nil | [12 empty] | Salaries paid | Nil | 150000 | 0 | 0 | Accountant
Action 2: Development impact: Support independent evaluation \ DLI Action: 2
Sub-Action 2a: Mid-term Evaluation
Activity 1: Prepare for visit of independent external evaluation of development | To be determined by the AAU and World Bank | Nil | [12 empty] | To be determined by the AAU and World Bank | Nil | 0 | 0 | 0 | All centre team members
Action 3: Strengthen excellence in educational programmes \DLI Action: 3
Sub-Action 3a: Curriculum Development
Activity 1: Curriculum review/development workshop involving regional/international partners for new M.Sc. and PhD Programme Curricula in Maternal and Child Health nursing | 2 days workshop and 2 weeks face-to-face meetings to develop the curricular for the 2 programs (M.Sc and PhD in Maternal and Child Health Nursing | Academic partners in Nursing | [12 empty] | Curricular developed | Nil | 10000 | 0 | 5000 | Deputy Centre Leader
Activity 2: Submit reviewed curricular to University Senate for approval | Apply for approval of 2 curricular from UNIBEN senate for upward review by NUC | Nil | [12 empty] | Curricular approved by UNIBEN Senate | Nil | 0 | 0 | 0 | Deputy Centre Leader
Sub-Action 3b: Short courses
Activity 1: Plan and implement 10 short courses in reproductive health in UNIBEN and partner institutions | CERHI and her partners will host short courses for at least 48 hours per short course | CERHI regional partners | [12 empty] | Short courses conducted | Nil | 60000 | 100000 | 15000 | Program Manager and M&E Officer
Sub-Action 3c: Student enrollment
Activity 1: Program marketing and Students’ enrolment | Place adverts on newspaper, radio gingles, television, website, share leaflets with partners | CERHI national and regional partners | [12 empty] | National and regional students enrolled | Nil | 20000 | 100000 | 0 | Program Manager and M&E Officer
Activity 2: Production of office administrative/academic materials, students’ handbook, Stationeries, Internet Communication, bills, Bank Charges etc. | Printing of students' handbooksand other administrative activities | Nil | [12 empty] | Administrative activities completed | Nil | 20000 | 0 | 0 | Program Manager and M&E Officer
Action 4: Strengthen teaching and learning excellence \DLI Action: 4
Sub-Action 4a: Accreditation
Activity 1: Undertake resource verification of new masters and PhD Programmes in Nursing | NUC will conduct resource verification for the 2 nursing programmes | Nil | [12 empty] | Resource verification conducted | Nil | 0 | 0 | 0 | Deputy Centre Leader
Activity 2: Undertake national accreditation of new masters and PhD Programmes in Nursing | NUC will send experts to conduct accreditation assessment for the 2 nursing programmes | Nil | [12 empty] | National accreditation received | Nil | 10000 | 100000 | 0 | Deputy Centre Leader
Activity 3: Undertake self-assessment following international standards | The Centre will identify an international accrediting body and will conduct self assessment for the 2 programmes | Academic partners in Nursing | [12 empty] | Self assessment completed | Nil | 30000 | 50000 | 0 | Centre Leader
Activity 4: Upgrade new courses and programmes to meet international standards | Apply and complete international accreditation requirements for the 2 nursing programmes | Academic partners in Nursing | [12 empty] | International accreditation received | Nil | 40000 | 200000 | 0 | Centre Leader
Sub-Action 4b: Publications
Activity 1: Support International research publication with national partners | Joint research publications by faculty, students and partners | National academic and industry partners | [12 empty] | Publications done with national partners | Nil | 30000 | 50000 | 15000 | Centre Leader
Activity 2: Support International research publication with regional/international partners | Joint research publications by faculty, students and partners | Regional/international academic and industry partners | [12 empty] | Publications done with regional and international partners | Nil | 15000 | 50000 | 5000 | Centre Leader
Sub-Action 4c: Improving teaching and lerning methods
Activity 1: Improving faculty teaching methods and faculty development (Equip participating departments with teaching and learning materials) | Purchase of printers, inks, photocopiers, stationeries and general equipment repairs for participating departments | Nil | [12 empty] | Participating departments equipped to face daily work | Nil | 25000 | 0 | 0 | Program Manager
Activity 2: Alternate power: generator, diesel tank, solar power with installation for international students’ hostel | 24/7 power supply for students at the hostel to improve their living conditions | Nil | [12 empty] | Generator bought and installed | Nil | 10000 | 0 | 0 | Procurement Officer
Activity 3: Alternate power: generator, diesel tank, solar power with installation for CERHI Faculty Guest house | 24/7 power supply for visiting faculty at theCERHI guest house to improve their living conditions | Nil | [12 empty] | Generator bought and installed | Nil | 10000 | 0 | 0 | Procurement Officer
Sub-Action 4d: CERHI building extension
Activity 1: Design and approve plan for two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | Approved plan | Nil | [12 empty] | Structural and electrical plans approved | Nil | 5000 | 0 | 0 | Procurement Officer
Activity 2: Completion of foundation works for two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | Completion of foundation works | Nil | [12 empty] | Foundation completed | Nil | 50000 | 0 | 0 | Procurement Officer
Activity 3: Completion of construction of two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | Completion of construction works | Nil | [12 empty] | Building completed | Nil | 100000 | 0 | 0 | Procurement Officer
Activity 4: Furnishing and equipping of two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | Furnishing and equipping | Nil | [12 empty] | Furnishing and equipping completed | Nil | 145000 | 300000 | 0 | Procurement Officer
Action 5: Enhancing relevance of Education & Research \DLI Action: 5
Sub-Action 5a: Internships
Activity 1: Plan and organize merit-based local/regional/international internship placements for staff | Identify industries and send staff for atleast 1 month internship | Industry partners | [12 empty] | Staff completes internship | Nil | 20000 | 50000 | 0 | Program Manager
Activity 2: Plan and organize merit-based local/international internship placements for students | Identify industries and send students for atleast 1 month internship | Industry partners | [12 empty] | Students completes internship | Nil | 40000 | 70000 | 0 | Program Manager
Sub-Action 5b: Research
Activity 1: Support entrepreneurship, innovations and patents | Support student and faculty research commercialization and patency | Academic and Industry partners | [12 empty] | Innovative researches developed | Nil | 40000 | 100000 | 0 | Centre Leader
Activity 2: Organize proposal writing, research methodology and publications workshop for students and faculty. | Once a year | Academic and Industry partners | [12 empty] | Workshop conducted | Nil | 10000 | 0 | 0 | Centre Leader
Activity 3: Support for regional and international conference attendance and manuscript preparation by students and faculty | As and when due | Academic and Industry partners | [12 empty] | Conferences attended | Nil | 50000 | 0 | 0 | Program Manager
Activity 4: Support 4 multidisciplinary team to develop regional research collaborations | Proposal presentations and team selections will be carried out | Academic and Industry partners | [12 empty] | Multidisciplinary teams identified and equipped | Nil | 60000 | 20000 | 0 | Deputy Centre Leader
Action 6: Fiduciary Enhancement \DLI Action: 6
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Support timely fiduciary reporting | Reporting | Nil | [12 empty] | Timely report submitted | Nil | 2000 | 15000 | 0 | Accountant
Activity 2: Support for the Internal audit system | Auditing | Nil | [12 empty] | Audit review conducted | Nil | 2000 | 15000 | 0 | Accountant
Activity 3: Web transparency on fiduciary reports | Web links | Nil | [12 empty] | Web links sent to World Bank for confirmation | Nil | 2000 | 15000 | 0 | Accountant
Activity 4: Support the procurement planning process | Annual Procurement plans | Nil | [12 empty] | Procurement plans completed | Nil | 2000 | 15000 | 0 | Accountant
Action 7: Institutional Impact \DLI Action: 7
Sub-Action 7a: Fiduciary Enhancement
Activity 1: Support UNIBEN to review strategic plan | Revised 5 year strategic plan for the university of Benin by experts and workshop dessimination of the strategic plan to stakeholders | Academic and Industry partners | [12 empty] | Strategic plan reviewed and disseminated | Nil | 20000 | 50000 | 0 | UNIBEN team
Activity 2: Support University to set-up a fundraising office | Create a Directorate of Research and Grant Management | Nil | [12 empty] | Directorate created | Nil | 20000 | 50000 | 0 | Centre Leader
Activity 3: Undertake self-assessment following international standards for institutional accreditation | self assessment done by Committee for UNIBEN in preparation for institutional accreditation | Academic and Industry partners | [12 empty] | Self assessment completed | Nil | 20000 | 50000 | 0 | UNIBEN team
[15 empty] | GRAND TOTAL |  | 1388000 | 1400000 | 55000
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus