## WORKS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦400 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN,NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2022– December, 2022
WORKS
2. | Prior Review Threshold:
| Procurement Method | Threshold for use of Method (US$) | Prior review Threshold (US$) | Comments
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Completion of foundation works for two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | WB | 50000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | N/A | N/A | N/A | 18th-Feb-22 | 18th-Sept-22 | 4.3
Actual
| Completion of construction of two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | WB | 100000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | N/A | N/A | N/A | 18th-Feb-22 | 18th-Sept-22 | 4.3
Actual
| Re-roofing and re-painting of CERHI complex | WB | 20000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | N/A | N/A | N/A | 18th-Feb-22 | 18th-Sept-22
Actual
| Total Cost |  | 170000
Note on B30: VIVIAN: The Directorate of Physical Planning of the University wiill assign Architects, Engineers etc to supervise the construction from start to finish

## GOODS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦400 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2022– December, 2022
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR | REMARKS
LOT 1 STAND-BY GENERATOR
| Alternate power: generator, diesel tank, solar power with installation for international students’ hostel | WB | 10000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 10000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
| Alternate power: generator, diesel tank, solar power with installation for CERHI Faculty Guest house | WB | 10000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 10000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
LOT 2 STATIONERY, LECTURE MATERIALS
| Production of office administrative/academic materials, students’ handbook, Stationeries, Internet Communication, bills, etc. | WB | 20000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 20000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
| Improving faculty teaching methods and faculty development (Equip participating departments with teaching and learning materials) | WB | 25000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 25000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
| Support the printing of hardcopies of the regional strategic plan | WB | 5000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 25000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
LOT 3 FURNISHING
| Furnishing and equipping of two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | WB | 145000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 145000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
LOT 4 ONLING SUBSCRIPTIONS
| Annual Subscription of NgREN |  | 100000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 20000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
| Annual subscription of EBSCOHOST |  | 15000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 15000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
Actual
| Annual subcription of Science-Direct |  | 15000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-22 | 7th-Feb-22 | Plan | N/A | N/A | 9th-march-22 | 9th-April-22 | 2022-05-17 | N/A | 15000 | 11th-June-22 | 11th-June-22 | 18th-June-22 | 18th-July-22
| TOTAL |  | 345000
NOTE:
1. In LOT1, LOT2 and LOT 3, we will apply the shopping procurement method since these items are off-shelf items and would be carried out more than once as needed.
Note on C42: VIVIAN: This does not include laboratory equipment. CERHI already won a grant from Seeding Labs to provide equipments that will be situated in the proposed laboratory space.

## CONSULTANCY SERVICES
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦400 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2022– December, 2022
CONSULTANCY SERVICES
2. | Prior Review Threshold:
Consultants (see Note 3)
|  |  | Threshold | Prior review
| Procurement Method |  | for use of Method | Threshold | Nature of Goods
|  |  | (US$) | (US$)
| 1. Quality and Cost Based Selection (QCBS) |  | N/A | N/A
| 2. Consultants Qualification Selection (CQS) |  | N/A | N/A
| 3. Least Cost Selection (LCS) |  | N/A | N/A
| 4. Fixed Budget Selection (FBS) |  | N/A | N/A
| 5. Selection of Individual Consultants (SIC) |  | N/A | N/A
| 6. Single Source Selection (SSS) |  | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule | [8 empty] | Request for Expression of Interest |  |  |  |  | Request for Proposal & Short List |  | Proposals |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Assignment | Source of Funds | Estimated Amount (US$) | Selection Method | Prior/Post Review | Lumpsum or Timed-Based | Plan vs. Actual | Submission Date | No-objection Date | Date Published | Submission Date | Plan vs. Actual | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) & (F) | Submission Negotiations Report | No-objection Award & Negotiations | Plan vs. Actual | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
Actual
| Establish faculty-wide ICT-based Learning Management Systems (LMS) in collaborating faculty and College | WB | 80000 | SSS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-22 | 12th-Oct-22 | NA | NA | NA | NA | NA
Actual
| Plan and implement 5 short courses in reproductive health in UNIBEN and partner institutions | WB | 60000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-22 | 12th-Oct-22 | N/A | N/A | N/A | N/A | N/A
Actual
| Undertake resource verification and national accreditation of new masters and PhD Programmes in Nursing | WB | 30000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-22 | 12th-Oct-22 | N/A | N/A | N/A | N/A | N/A
Actual
| Undertake self-assessment following international standards | WB | 30000 | SSS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-22 | 12th-Oct-22 | NA | NA | NA | NA | NA
| Upgrade new courses and programmes to meet international standards | WB | 40000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-22 | 12th-Oct-22 | N/A | N/A | N/A | N/A | N/A
| Design and approve plan for two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | WB | 5000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-21 | 12th-Dec-21 | N/A | N/A | N/A | N/A | N/A
| Total Cost |  | 245000
Note
|  | Please note that the yellow cells do not require dates, as the project would not be required to send to the WB for Clearance. | [6 empty] | Project should replace the dates with Not Applicable " NA".
1
2

## Simplified P plan (hidden)
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017–December, 2017
OPERATING COST
2. | Prior Review Threshold:
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A | N/A
| 2. NCB (Goods) | N/A | N/A | N/A
| 1. ICB (Works) | N/A | N/A | N/A
| 4. NCB (Works) | N/A | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A | N/A
| 6. Shopping | N/A | N/A | N/A
| 7. Direct Contracting | N/A | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [6 empty] | DISBURSEMENT LINKED INDICATORS
| Description of Expenses | Source of Funds | Estimated Amount (US$) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter | Total Amount (US$) | Plan Vs Actual | DLI/DLR
| Audit expenses (Procurement and Account audit) | WB | 17500 | 3000 | 4000 | 3000 | 7500 | 17500 | Plan
Actual
| Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | WB | 30000 | 6000 | 7500 | 10500 | 6000 | 30000 | Plan
Actual
| Student recruitment (Advertisements, portal, travels, interview and printing) | WB | 13500 | 3000 |  | 7000 | 3500 | 13500 | Plan
Actual
| Scaling up PhD Programmes (increasing students numbers,visiting and professors and researchers) Honoraria of non employed staff) | WB | 36000 | 6000 | 9000 | 13500 | 7500 | 36000 | Plan
Actual
| International Research Collabration and Joint Research Programme among students faculties | WB | 60000 | 11000 | 15000 | 22500 | 11500 | 60000 | Plan
Actual
| Local Travels | WB | 24000 | 5000 | 6000 | 9000 | 4000 | 24000 | Plan
Actual
| Faculty Developments :capacity building in curricala and non based programmes | WB | 50000 | 9000 | 12500 | 19000 | 9500 | 50000 | Plan
Actual
| Research grant pools (to small and medium scale applied research) | WB | 225000 | 5000 | 5000 | 8500 | 4500 | 225000 | Plan
Actual
| Publication in high impact factor journals by faculty and students (cost of publication) | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | WB | 10500 | 2000 | 2500 | 4000 | 2000 | 10500 | Plan
Actual
| Provide equitable distribution of excellent high quality open and distant learning | WB | 35000 | 6000 | 8750 | 13500 | 6750 | 35000 | Plan
Actual
| Provide equitable distrbution of excellence and high quality research by instituting doctoral research | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| provide broad-based scientific capacity of students through intenships, short courses and SIWES | WB | 40000 | 7000 | 10000 | 15000 | 8000 | 40000 | Plan
Actual
| Provision of extension and community mobilization services/awareness | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Ensure social relevance through annual regional stakeholders meeting in participating countries NRCRI | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
| Engagement in joint research project among participating institutions | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Introdution of regional working groups for research groups | WB | 16000 | 3000 | 6000 | 4000 | 3000 | 16000 | Plan
Actual
| Short term exchange programmes within Nigeria | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Schorlaships research for Cefter Students and | WB | 150000 | 30000 | 35000 | 55000 | 30000 | 150000 | Plan
Actual
| Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Research grant pools to support faculty and student's international applied research on post-harvest losses | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Workshop at AOCAY partner. | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Development joint curricula among partnership institution and CEFTER departments | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Identification of joint training needs for academic and professional staff in post-harvest science and management | WB | 12000 | 2000 | 3000 | 4500 | 2500 | 12000 | Plan
Actual
| Stakeholders meeting to review progress at ACE | WB | 12000 | 2000 | 3000 | 5000 | 2000 | 12000 | Plan
Actual
| Domestication of curricula in the departments at BSU (Independent review of draft curricula) | WB | 6000 | 1000 | 1500 | 2000 | 1500 | 6000 | Plan
Actual
| Faculty and students training (Staff on PG fellowship) | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | WB | 15000 | 3500 | 4000 | 4500 | 3000 | 15000 | Plan
Actual
| Institute lecture series: NSPRI organised on Impact of Climate change on PHL | WB | 10000 | 2500 | 2500 | 3000 | 2000 | 10000 | Plan
Actual
| Produce and circulate monographs targeted at awareness creation and extension to rural farmers | WB | 6000 | 1000 | 2000 | 2500 | 500 | 6000 | Plan
Actual
| Support Research fellowships( Sponsor staff of partner institutions on PG programs) | WB | 15000 | 3500 | 3500 | 6000 | 2000 | 15000 | Plan
Actual
| Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | WB | 35000 | 6000 | 6000 | 15000 | 8000 | 35000 | Plan
Actual
| Start long faculty exchanges between CEFTER, and Universities in Africa | WB | 24000 | 5000 | 6000 | 10000 | 3000 | 24000 | Plan
Actual
| Start of joint research projects between CEFTER,universties and research insttutes elsewhere in Africa | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
Actual
| Produce operational manuals for students | WB | 6000 |  |  | 3000 | 3000 | 6000 | Plan
Actual
| Monitoring and evaluation (Travels, stationaries) | WB | 18000 | 4000 | 4500 | 7000 | 2500 | 18000 | Plan
Actual
| Fund raising activities (Meetings, travels, media) | WB | 10500 | 3000 | 2500 | 4500 | 1500 | 10500 | Plan
Actual
| NgREN Communication Services | WB | 300000 | 60000 | 50000 | 130000 | 60000 | 300000 | Plan
Actual
| Casual staff on Utility services (Cleaners, security) | WB | 40000 | 8000 | 10000 | 14000 | 8000 | 40000 | Plan
Actual
| Provide Automated accounting System | WB | 20000 | 4500 | 6000 | 6500 | 3000 | 20000 | Plan
Actual
|  | TOTAL | 1429000 | 238000 | 275750 | 480500 | 240250 | 1429000
NOTE:
1. operating manuals for students are produced every year.

## Operating Cost
SUB-COMPONENT | ACTIVITIES
Component 1: Strengthening Africa Centers of Excellence
Activity No | ACIVITIES | ESTIMATED BUDGET ($)
Component 1: Strengthening Africa Centers of Excellence
1 | Weekly meetings of Project Management Committee Members | 2000
2 | Bi-Annual meeting of Industry and Sectoral Advisory Board members | 5000
3 | Annual meeting of International Advisory Board members | 13000
4 | Participate in 2 Regional ACE workshops by Project staff | 60000
5 | Renew/ establish partnership and develop MOU with Partners | 10000
6 | Stipends to regional students | 150000
7 | Salaries for project staff | 150000
8 | Administrative expenses | 100000
9 | Program marketing and Students’ enrolment | 20000
10 | Support participating departments with resources for teaching and external examinations | 40000
11 | Conduct orientation workshops for new students | 10000
12 | Provide student permits for 20 regional students | 10000
13 | Provide reproductive health textbooks and journals for CERHI library | 20000
14 | Support International research publication with national partners | 30000
15 | Support International research publication with regional/international partners | 15000
16 | Plan and organize merit-based local/regional/international internship placements for staff | 20000
17 | Plan and organize merit-based local/international internship placements for students | 40000
18 | Support entrepreneurship, innovations and patents | 40000
19 | Organize proposal writing, research methodology and publications workshop for students and faculty. | 10000
20 | Support for regional and international conference attendance and manuscript preparation by students and faculty | 50000
21 | Support 4 multidisciplinary team to develop regional research collaborations | 60000
22 | Provide start-up grants for proposed patents for faculty and students | 100000
23 | Support timely fiduciary reporting | 2000
24 | Support for the Internal audit system | 2000
25 | Web transparency on fiduciary reports | 2000
26 | Support the procurement planning process | 2000
27 | Conduct dessimination one workshop of the regional strategic plan for external and internal stakeholders of the university | 10000
28 | Fill the gaps identified during the self-assessment by the Quality Assurance Agency for Higher Education, UK and submit report to the them | 20000
29 | Undertake institutional accreditation with QAA | 200000
1193000

## SUMMARY
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
UNIVERSITY OF BENIN, EDO STATE
SUMMARY
THE EXCHANGED RATE USED IS ₦400 PER US DOLLAR
GOODS
| LOT 1 STAND-BY GENERATOR | 20000
| LOT 2 : LABORATORY EQUIPMENT | 200287.71
| LOT 2 STATIONERY, LECTURE MATERIALS | 50000
| LOT 3 FURNISHING | 145000
| LOT 4 ONLING SUBSCRIPTIONS | 130000
TOTAL |  |  | 345000
WORKS |  |  | 170000
| CONSULTANCY SERVICES |  | 245000
OPERATING COST |  |  | 1193000
GRAND TOTAL |  |  | 1953000