## CERHI
Name of Center | CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
Institution | UNIVERSITY OF BENIN |  |  | On Schedule
Country | NIGERIA
Center Leader | PROFESSOR FRIDAY OKONOFUA |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2023 - DECEMBER 2023
Work Plan Activities | Description | Partner Contribution (if relevant) | 2023 Y2Q1 |  |  | 2023 Y2Q2 |  |  | 2023 Y2Q3 |  |  | 2023 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Develop and support centre governance, structure and strategy \ DLI Action: 1
Sub-Action 1a: Meetingsand Partnerships
Activity 1: Bi-Weekly meetings of Project Management Committee Members | Once in 2 weeks meetings | Nil | [12 empty] | Bi-weekly meetings conducted | Nil | 2000 | 0 | 0 | Program Manager
Activity 2: Bi-Annual meeting of Industry and Sectoral Advisory Board members | Twice a year | All academic, industry and sectoral partners | [12 empty] | Bi-annual meet\ings conducted | Nil | 5000 | 0 | 0 | Project Coordinator
Activity 3: Annual meeting of International Advisory Board members | Once a year | All international academic partners | [12 empty] | Annual meeting conducted | Nil | 13000 | 0 | 0 | Centre Leader
Activity 4: Participate in 2 Regional ACE workshops by Project staff | Twice a year | All centres, experts and AAU and World Bank staff | [12 empty] | Project staff attend 2 ACE regional meetings | Nil | 60000 | 0 | 0 | Program Manager
Activity 5: Renew/ establish partnership and develop MOU with Partners | Continuous activity | All centre partners and new ones | [12 empty] | Patnerships renewed | Nil | 10000 | 0 | 15000 | Deputy Centre Leader
Sub-Action 1b: Internet and E-books and Journals subscription
Activity 1: Annual Subscription of NgREN | Payment for annual subscription | Nil | [12 empty] | NgREN subscibed | Nil | 30000 | 0 | 0 | Program Manager
Activity 2: Annual subscription of EBSCOHOST | Payment for annual subscription | Nil | [12 empty] | EBSCOHOST subscribed | Nil | 15000 | 0 | 0 | Program Manager
Activity 3: Annual subcription of Science-Direct | Payment for annual subscription | Nil | [12 empty] | Science-Direct subscribed | Nil | 15000 | 0 | 0 | Program Manager
Sub-Action 1c: Administrative Activities
Activity 1: Stipends to regional students | Monthly stipends to for over 40 regional students (PhD and MSc) to cover feeding and other living expenses | Nil | [12 empty] | Stipends paid | Nil | 150000 | 0 | 0 | Accountant
Activity 2: Salaries for project staff | Monthly salaries for externally hired staff (Program Manager, Assistant Program Manager, Web Master/Communication Officer, M&E Assistants, Corp Members and Janitors) | Nil | [12 empty] | Salaries paid | Nil | 150000 | 0 | 0 | Accountant
Activity 3: Administrative Expenses | Reagents for research laboratory, stationeries, maintenance and repairs of office equipment, CERHI complex, guest house and hostel maintenance and repairs, diesel for generator, fuelling and maintenance of CERHI bus. | Nil | [12 empty] | Smooth running of the project | Nil | 100000 | 0 | 0 | Program Manager
Activity 4: Repair of CERHI complex roof | Repairs | Nil | [12 empty] | Safe and comfortable working environment | Nil | 20000 | 0 | 0 | Procurement Officer
Action 2: Development impact: Support independent evaluation \ DLI Action: 2
Sub-Action 2a: Mid-term Evaluation
Activity 1: Prepare for visit of independent external evaluators for mid term review | To be determined by the AAU and World Bank | Nil | [12 empty] | To be determined by the AAU and World Bank | Nil | 0 | 0 | 0 | All centre team members
Action 3: Strengthen excellence in educational programmes \DLI Action: 3
Sub-Action 3a: Student enrollment
Activity 1: Program marketing and 70 Students’ enrolment | Place adverts on newspaper, radio gingles, television, website, share leaflets with partners | CERHI national and regional partners | [12 empty] | National and regional students enrolled | Nil | 20000 | 100000 | 0 | Program Manager and M&E Officer
Activity 2: Production of office administrative/academic materials, students’ handbook, Stationeries, Internet Communication, bills, Bank Charges etc. | Printing of students' handbooksand other administrative activities | Nil | [12 empty] | Administrative activities completed | Nil | 20000 | 0 | 0 | Program Manager and M&E Officer
Sub-Action 3b: Student support
Activity 1: Support participating departments with resources for teaching and external examinations | Allowance for services rendered, equipment maintenance etc | nil | [12 empty] | Departments equiped with needed resources | Nil | 40000 | 0 | 5000 | Deputy Centre Leader
Activity 2: Conduct orientation workshops for new students | Centre staff and faculty will provide detailed information about the school and programs | Nil | [12 empty] | Orientation workshop conducted | Nil | 10000 | 0 | 0 | Deputy Centre Leader
Activity 3: Provide student permits for regional students |  | Nil | [12 empty] | Permits given to regional students | Nil | 10000 |  |  | Program Manager
Activity 4: Provide reproductive health textbooks and journals for CERHI library | Anuual subscription for reproductive health journals and books | Nil | [12 empty] | CERHI library updated with new textbooks and journals for faculty and students consumption | Nil | 20000 |  |  | CERHI Librarian
Sub-Action 3c: Short courses
Activity 1: Plan and implement 2 short courses in reproductive health in UNIBEN and partner institutions | CERHI and her partners will host short courses for at least 48 hours per short course | CERHI regional partners | [12 empty] | Short courses conducted | Nil | 60000 | 100000 | 15000 | Program Manager and M&E Officer
Action 4: Strengthen teaching and learning excellence \DLI Action: 4
Sub-Action 4a: Publications
Activity 1: Support International research publication with national partners (payment for journal publications) | Joint research publications by faculty, students and partners | National academic and industry partners | [12 empty] | Publications done with national partners | Nil | 30000 | 50000 | 15000 | Centre Leader
Activity 2: Support International research publication with regional/international partners (payment for journal publications) | Joint research publications by faculty, students and partners | Regional/international academic and industry partners | [12 empty] | Publications done with regional and international partners | Nil | 15000 | 50000 | 5000 | Centre Leader
Sub-Action 4b: Improving teaching and lerning methods
Activity 1: Improving faculty teaching methods and faculty development (Equip participating departments with teaching and learning materials) | Purchase of printers, inks, photocopiers, stationeries and general equipment repairs for participating departments | Nil | [12 empty] | Participating departments equipped to face daily work | Nil | 25000 | 0 | 0 | Program Manager
Activity 2: Alternate power: generator, diesel tank, solar power with installation for international students’ hostel | 24/7 power supply for students at the hostel to improve their living conditions | Nil | [12 empty] | Generator bought and installed | Nil | 30000 | 0 | 0 | Procurement Officer
Sub-Action 4c: CERHI building extension
Activity 1: Furnishing and equipping of two theatre halls, offices, space for simulation laboratory and space for molecular laboratory | Furnishing and equipping | Nil | [12 empty] | Furnishing and equipping completed | Nil | 200000 | 50000 | 0 | Procurement Officer
Activity 2: Simulation equipment and technical support | manikins | Nil | [12 empty] | Manikins |  | 100000 |  |  | Centre Leader
Action 5: Enhancing relevance of Education & Research \DLI Action: 5
Sub-Action 5a: Revenue generation
Activity 1: Promote and support grant writing by staff and faculty | Grant officer to identify available grants and inform faculty and students | Nil | [12 empty] | Grants received by CERHI | Nil | 20000 | 0 | 0 | Program Manager
Activity 2: Improve CERHI's internal revenue generation by implementing activities in the business plan | The business plan of CERHI implemented | Industry partners | [12 empty] | project sustained | Nil | 0 | 0 | 0 | Program Manager
Sub-Action 5b: Internships
Activity 1: Plan and organize merit-based local/regional/international internship placements for 4 staff | Identify industries and send staff for atleast 1 month internship | Industry partners | [12 empty] | Staff completes internship | Nil | 20000 | 50000 | 0 | Program Manager
Activity 2: Plan and organize merit-based local/international internship placements for 200 students | Identify industries and send students for atleast 1 month internship | Industry partners | [12 empty] | Students completes internship | Nil | 40000 | 70000 | 0 | Program Manager
Sub-Action 5c: Enterpreneurship and Innovation
Activity 1: Review of job descriptions for TTO staff | From the background, the job description of TTO staff needs to be reviewed because there is little or no activity being carried out apart from plagiarism tests | Nil | [12 empty] | Job description reviewed | Nil | 1000 |  |  | Committee Chairperson
Activity 2: Capacity building training for IPTTO staff by international and national technology transfer experts | Atleast, 20 TTO staff needs to be trained by national and regional technology transfer experts | Nil | [12 empty] | Training conducted | Nil | 8000 |  |  | Committee Chairperson
Activity 3:Reviewing and approval of IPTTO policy including operational strategy by university management | The current draft IPTTO policy of the university needs to be revised and approved by management so that it can be placed on the university's website and also to be implemented | Nil | [12 empty] | Policy approved | Nil | 1000 |  |  | Committee Chairperson
Activity 4: Identify and strengthen links with national and international collaborators |  | Nil | [13 empty] | Nil |  |  |  | Committee Chairperson
Activity 5: Sign/ renew MoUs with national and international partners (ie Japanese Patent Office, NOTAP, WIPO) | Atleast 3 MoUs will be signed with identified bodies and strong collaboration will kick start and maintained | Nil | [12 empty] | MoUs signed | Nil |  |  |  | Committee Chairperson
Activity 6: Orientation and re-orientation of university staff and students on functions of the IPTTO | There is need to create awareness to the university community on the functions of the TTO office. The orientation will be conducted twice during the period of the year | Nil | [12 empty] | Orientation workshop conducted | Nil | 3000 |  |  | Committee Chairperson
Activity 7: Establish partnership with technology hubs | Atleast 1 hub will be identified and partnered with to support the TTO | Nil | [12 empty] | Signed agreements done | Nil |  |  |  | Committee Chairperson
Activity 8: Deployment and integration of updated technological solutions to the TTO’s operations. | There is need to equip the TTO office with modern softwares, databases to aid their work. Some of the softwares are subcribed annually | Nil | [12 empty] | High impact technology received | Nil | 15000 |  |  | Committee Chairperson
Activity 9: Set-up a seven (7) member committee whose terms of reference will be to; | There is need to have a committee to coordinate activities listed in this module | Nil | [12 empty] | Committee conducted | Nil | 0 |  |  | Centre Leader CERHI
Activity 9a: Conduct a needs assessment survey | Needs assessment survey is required to ascertain the needs and skills to be used in developing the postgraduate curricula | Nil | [12 empty] | Needs assessment done | Nil | 2000 |  |  | Committee Chairperson
Activity 9b: Identify and engage stakeholders/faculty | Stakeholders and faculty to teach or train students must be identified | Nil | [12 empty] | Stakeholders engaged | Nil | 0 |  |  | Committee Chairperson
Activity 9c: Develop curricula with stakeholders | As required by the module, an enriched innovative and entrepreneurship curriculum will be developed | Nil | [12 empty] | Curricula developed | Nil | 2000 |  |  | Dean of PG School and Committee
Activity 9d: Submit report of needs assessment and draft curricula to CERHI | CERHI project team will review all reports to ensure that they align with the goal of the centre | Nil | [13 empty] | Nil | 0 |  |  | Dean of PG School and Committee
Activity 9e: CERHI team will conduct independent review of the curricula | CERHI project team will review all reports to ensure that they align with the goal of the centre | Nil | [13 empty] | Nil | 0 |  |  | CERHI PMC
Activity 9f: Approve curricula for implementation starting from 2022/2023 session | The revised curricula must be approved by the university management before it can be part of the post graduate program at CERHI | Nil | [13 empty] | Nil | 0 |  |  | Dean of PG School and Vice Chancellor
Activity 9g: Train faculty and students using curricula | All CERHI students will undergo atleast one course in entrepreneurship before graduation | Nil | [12 empty] | Faculty trained | Nil | 0 |  |  | PG Coordinators and Heads of Department
Activity 10: Set up a committee to develop a proposal for the establishment of the endowment fund | A sub-committee from the 2.1.1a above will develop the proposal which will serve as a guide for the seed grant fund | Nil | [12 empty] | Committee conducted | Nil | 0 |  |  | Vice Chancellor/ Centre Leader
Activity 11: Set up a fund management board | A sub-committee from the 2.1.1a above will form the fund management board to guide and monitor funds given out as seed grants | Nil | [13 empty] | Nil | 0 |  |  | Vice Chancellor/ Centre Leader
Activity 12: Revise CERHI research proposal template to contain ‘impact of the research’ | CERHI already has a research proposal template, but there is need to improve the template to contain activities about impact and sustainability. | Nil | [13 empty] | Nil | 0 |  |  | Committee Chairperson
Activity 13: Review submitted research proposals and use set guidelines to select successful proposals | Using set guidelines, the committee will revise submitted proposals and streamline them to the best 3 that will be funded | Nil | [13 empty] | Nil | 500 |  |  | Committee Chairperson
Activity 14: Award at-least 3 seed grants to successful proposals | The 3 best research proposals will be supported with seed grants to start up | Nil | [13 empty] | Nil | 45000 |  |  | Fund Management Committee
Activity 15: Monitor on-going research | The committee will also monitor the research supported with the seed grants | Nil | [13 empty] | Nil | 0 |  |  | Fund Management Committee
Activity 16: Set-up a capacity building workshop organizing committee | Athere is need to have a committee to coordinate the workshops | Nil | [13 empty] | Nil | 0 |  |  | CERHI, Program Manager, Research Coordinator
Activity 17: Develop concept note and agenda for workshops | The concept note will guide the proposed workshops | Nil | [13 empty] | Nil | 1500 |  |  | Committee Chairperson
Activity 17: Identification of resource persons to teach during the workshops | Qualified resource persons to teach during the workshops is required | Nil | [13 empty] | Nil | 0 |  |  | Committee Chairperson
Activity 18: Organize quarterly (3) workshops (all hybrid) in 2022 | The university staff and students require more knowledge on technology transfer and commercialization to guide their research | Nil | [13 empty] | Nil | 15000 |  |  | Committee Chairperson
Activity 19: Constitute a sector-focused incubator team that will do the following; | There is need to have a team to coordinate the module | Nil | [13 empty] | Nil | 0 |  |  | Vice Chancellor /CERHI Project Management team
Activity 19a: Conduct feasibility studies | There is need to conduct feasibilty studies to understand what is available and what to plan for | Nil | [13 empty] | Nil | 3000 |  |  | Team leader
Activity 19b: identify stakeholders | Collaborative stakeholders are required for the module to be successful | Nil | [13 empty] | Nil | 0 |  |  | Team leader
Activity 19c: develop a business plan for the incubator, | The team will develop a business plan that will guide the sustainable activities of the incubator | Nil | [13 empty] | Nil | 3000 |  |  | Team leader
Activity 19d: The centre team will review the plan | The business plan will be reviewed and finalized | Nil | [13 empty] | Nil | 0 |  |  | Team leader
Activity 19e: Approval and implementation of the plan | The business plan will be approved by management and the university will take it as a guide for their future incubator set-up | Nil | [13 empty] | Nil | 0 | 0 | 0 | Team leader
Activity 20: Support for regional and international conference attendance and manuscript preparation by students and faculty | As and when due | Academic and Industry partners | [12 empty] | Conferences attended | Nil | 50000 | 0 | 0 | Program Manager
Activity 21: Support 4 multidisciplinary team to develop regional research collaborations | Proposal presentations and team selections will be carried out | Academic and Industry partners | [12 empty] | Multidisciplinary teams identified and equipped | Nil | 60000 | 20000 | 0 | Deputy Centre Leader
Activity 22: Provide start-up grants for proposed patents for faculty and students | Grants given to 5 groups/individuals for patenting or commercialization | Academic and Industry partners | [12 empty] | teams or individuals provided with grants | Nil | 100000 | 20000 | 0 | Deputy Centre Leader
Action 6: Fiduciary Enhancement \DLI Action: 6
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Update and submit Interim Financial Reports as and when due | Reporting | Nil | [12 empty] | Timely report submitted | Nil | 2000 | 15000 | 0 | Accountant
Activity 2: Support biannual Internal auditing and annual external auditting of CERHI account system and annual procurement audit. | Auditing | Nil | [12 empty] | Audit review conducted | Nil | 2000 | 15000 | 0 | Accountant and Procurement Officer
Activity 3: Upload all financial reports to CERHI website for transparency | Web links | Nil | [12 empty] | Web links sent to World Bank for confirmation | Nil | 2000 | 15000 | 0 | Accountant
Activity 4: Follow approved procurement rules in works, consultancy and supply of goods and services to the centre | Annual Procurement plans | Nil | [12 empty] | Procurement plans completed | Nil | 2000 | 15000 | 0 | Procurement Officer
Action 7: Institutional Impact \DLI Action: 7
Sub-Action 7a: Regional Strategy
Activity 1: Support the printing of hardcopies of the regional strategy | Revised 2 year regional strategy for the university of Benin by experts printed | Nil | [12 empty] | Strategic plan printed | Nil | 5000 | 50000 | 0 | UNIBEN team
Activity 2: Conduct dessimination workshop of the regional strategy for external and internal stakeholders of the university | 1 day workshop conducted | Academic and Industry partners | [12 empty] | Regional strategic plan disseminated | Nil | 10000 | 50000 | 0 | UNIBEN team
Sub-Action 7b: Institutional Accreditation
Activity 1: Fill the gaps identified during the self-assessment by the Quality Assurance Agency for Higher Education, UK and submit report to the them | Gap assessment completed successfully by UNIBEN Impact Committee in preparation for institutional accreditation | Academic and Industry partners | [12 empty] | Self assessment completed | Nil | 20000 | 50000 | 0 | UNIBEN team
Activity 2: Undertake institutional accreditation with QAA (Receive institutional accreditation by QAA) | Follow steps of the international accreditation stipulated by QAA | Nil | [12 empty] | International accreditation received | Nil | 200000 | 200000 | 0 | UNIBEN team
Sub-Action 7c: PASET Regional Benchmarking
Activity 1:Develop intervention plan based on the university ranking on the benchmarking assessment | Guidelines for the benchmarking activities will be used | Nil | [12 empty] | Benchmarking score passed | Nil | 0 | 0 | 0 | UNIBEN team
Activity 2: Undertakethe intervention plan activities as approved by the World Bank and AAU | Guidelines for the benchmarking activities will be used | Nil | [12 empty] | Benchmarking score passed | Nil | 10000 | 0 | 0 | UNIBEN team
[15 empty] | GRAND TOTAL |  | 1793000 | 920000 | 55000
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus