## WORKS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦756 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN,NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2024– December, 2024
WORKS
2. | Prior Review Threshold:
| Procurement Method | Threshold for use of Method (US$) | Prior review Threshold (US$) | Comments
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Total Cost |  | 0

## GOODS
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT
1. | General THE EXCHANGED RATE USED IS ₦756 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2024 – December, 2024
G O O D S
2. | Prior Review Threshold:
Goods and Non-Consulting (see Note 1)
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A
| 2. NCB (Goods) | N/A | N/A
| 1. ICB (Works) | N/A | N/A
| 4. NCB (Works) | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A
| 6. Shopping | N/A | N/A
| 7. Direct Contracting | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [7 empty] | Bid Documents |  | Bidding Period |  | Bid Evaluation |  | Contract Award |  |  | Contract Implementation |  |  | DISBURSEMENT LINKED INDICATORS
| Description of Contract | Source of Funds | Estimated Amount (US$) | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Expected Date Issue of Bid Docs | Expected Bid closing Date | Plan vs. Actual | Transmission Bid Docs Date | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report | No-objection Date | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR | REMARKS
LOT 1 STATIONERY, LECTURE MATERIALS
| Production of office administrative/academic materials, students’ handbook, Stationeries, Internet Communication, bills, etc. | WB | 20000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 20000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
Actual
| Improving faculty teaching methods and faculty development (Equip participating departments with teaching and learning materials) | WB | 25000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 25000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
| Provide reproductive health textbooks and journals for CERHI library | WB | 20000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 20000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
LOT 2 FURNISHING
| Simulation equipment and technical support | WB | 50000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 50000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
Actual
| Purchase of reagents and repairs of equipment in the molecular laboratory | WB | 50000 | SPM | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 50000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
Actual
LOT 3 ONLING SUBSCRIPTIONS
| Annual Subscription of NgREN |  | 30000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 30000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
Actual
| Annual subscription of EBSCOHOST |  | 15000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 15000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
Actual
| Annual subcription of Science-Direct |  | 15000 | SSS | Post- Qualification | N/A | Post Review | 9th-Jan-24 | 7th-Feb-24 | Plan | N/A | N/A | 9th-march-24 | 9th-April-24 | 2024-05-17 | N/A | 15000 | 11th-June-24 | 11th-June-24 | 18th-June-24 | 18th-July-24
| TOTAL |  | 225000
NOTE:
1. In LOT1, LOT2 and LOT 3, we will apply the shopping procurement method since these items are off-shelf items and would be carried out more than once as needed.

## CONSULTANCY SERVICES
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦756 PER US DOLLAR
| Country/Organisation: | UNIVERSITY OF BENIN, NIGERIA
| Project/Programme: | Center of Excellence in Reproductive Health Innovation (CERHI)
Loan No:
| Implementing Agency, Address: | UNIVERSITY OF BENIN, BENIN CITY, EDO STATE, NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2024– December, 2024
CONSULTANCY SERVICES
2. | Prior Review Threshold:
Consultants (see Note 3)
|  |  | Threshold | Prior review
| Procurement Method |  | for use of Method | Threshold | Nature of Goods
|  |  | (US$) | (US$)
| 1. Quality and Cost Based Selection (QCBS) |  | N/A | N/A
| 2. Consultants Qualification Selection (CQS) |  | N/A | N/A
| 3. Least Cost Selection (LCS) |  | N/A | N/A
| 4. Fixed Budget Selection (FBS) |  | N/A | N/A
| 5. Selection of Individual Consultants (SIC) |  | N/A | N/A
| 6. Single Source Selection (SSS) |  | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule | [8 empty] | Request for Expression of Interest |  |  |  |  | Request for Proposal & Short List |  | Proposals |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  |  | Contract Award |  |  | Contract Implementation |  | DISBURSEMENT LINKED INDICATORS
| Description of Assignment | Source of Funds | Estimated Amount (US$) | Selection Method | Prior/Post Review | Lumpsum or Timed-Based | Plan vs. Actual | Submission Date | No-objection Date | Date Published | Submission Date | Plan vs. Actual | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) & (F) | Submission Negotiations Report | No-objection Award & Negotiations | Plan vs. Actual | Contract Amount (US$) | Contract Award Date | Contract Signature Date | Start Date | End Date | DLI/DLR
| Plan and implement 2 short courses in reproductive health in UNIBEN and partner institutions | WB | 60000 | CQS | Post Review | Lumpsum | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | 8th-Jan-23 | 12th-Oct-23 | N/A | N/A | N/A | N/A | N/A
Actual
| Total Cost |  | 60000
Note
|  | Please note that the yellow cells do not require dates, as the project would not be required to send to the WB for Clearance. | [6 empty] | Project should replace the dates with Not Applicable " NA".
1
2

## Simplified P plan (hidden)
REVISED SIMPLIFIED PROCUREMENT PLAN FOR ACE PROJECT 2017
1. | General THE EXCHANGED RATE USED IS ₦200 PER US DOLLAR
| Country/Organisation: | BENUE STATE UNIVERSITY NIGERIA
| Project/Programme: | Center of Excellence in the control of post harvest losses(center for food technology and research)
Loan No:
| Implementing Agency, Address: | BENUE STATE UNIVERSITY,MAKURDI,NIGERIA
World Bank's Approval Date of Procurement Plan:
Date of General Procurement Notice:
| Period Covered by these Procurement Plans: | January, 2017–December, 2017
OPERATING COST
2. | Prior Review Threshold:
|  | Threshold | Prior review
| Procurement Method | for use of Method | Threshold | Comments
|  | (US$) | (US$)
| 1. ICB and LIB (Goods) | N/A | N/A | N/A
| 2. NCB (Goods) | N/A | N/A | N/A
| 1. ICB (Works) | N/A | N/A | N/A
| 4. NCB (Works) | N/A | N/A | N/A
| 5. ICB (Non-Consultant Services) | N/A | N/A | N/A
| 6. Shopping | N/A | N/A | N/A
| 7. Direct Contracting | N/A | N/A | N/A
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [6 empty] | DISBURSEMENT LINKED INDICATORS
| Description of Expenses | Source of Funds | Estimated Amount (US$) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter | Total Amount (US$) | Plan Vs Actual | DLI/DLR
| Audit expenses (Procurement and Account audit) | WB | 17500 | 3000 | 4000 | 3000 | 7500 | 17500 | Plan
Actual
| Employment and training technicians and qualified support staff (Training of staff on new equiptment and recruitment process fees) | WB | 30000 | 6000 | 7500 | 10500 | 6000 | 30000 | Plan
Actual
| Student recruitment (Advertisements, portal, travels, interview and printing) | WB | 13500 | 3000 |  | 7000 | 3500 | 13500 | Plan
Actual
| Scaling up PhD Programmes (increasing students numbers,visiting and professors and researchers) Honoraria of non employed staff) | WB | 36000 | 6000 | 9000 | 13500 | 7500 | 36000 | Plan
Actual
| International Research Collabration and Joint Research Programme among students faculties | WB | 60000 | 11000 | 15000 | 22500 | 11500 | 60000 | Plan
Actual
| Local Travels | WB | 24000 | 5000 | 6000 | 9000 | 4000 | 24000 | Plan
Actual
| Faculty Developments :capacity building in curricala and non based programmes | WB | 50000 | 9000 | 12500 | 19000 | 9500 | 50000 | Plan
Actual
| Research grant pools (to small and medium scale applied research) | WB | 225000 | 5000 | 5000 | 8500 | 4500 | 225000 | Plan
Actual
| Publication in high impact factor journals by faculty and students (cost of publication) | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Provide equitable distribution of excellence through affiliation to other institutions (Travels and mettings) | WB | 10500 | 2000 | 2500 | 4000 | 2000 | 10500 | Plan
Actual
| Provide equitable distribution of excellent high quality open and distant learning | WB | 35000 | 6000 | 8750 | 13500 | 6750 | 35000 | Plan
Actual
| Provide equitable distrbution of excellence and high quality research by instituting doctoral research | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| provide broad-based scientific capacity of students through intenships, short courses and SIWES | WB | 40000 | 7000 | 10000 | 15000 | 8000 | 40000 | Plan
Actual
| Provision of extension and community mobilization services/awareness | WB | 15000 | 3000 | 3500 | 5500 | 3000 | 15000 | Plan
Actual
| Ensure social relevance through annual regional stakeholders meeting in participating countries NRCRI | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
| Engagement in joint research project among participating institutions | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Introdution of regional working groups for research groups | WB | 16000 | 3000 | 6000 | 4000 | 3000 | 16000 | Plan
Actual
| Short term exchange programmes within Nigeria | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Schorlaships research for Cefter Students and | WB | 150000 | 30000 | 35000 | 55000 | 30000 | 150000 | Plan
Actual
| Introdution of short term (professional) courses (design special Agro Bussiness start-up courses for loan takers) | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Research grant pools to support faculty and student's international applied research on post-harvest losses | WB | 16000 | 3000 | 4000 | 6000 | 3000 | 16000 | Plan
Actual
| Workshop at AOCAY partner. | WB | 15000 | 3000 | 4000 | 5500 | 2500 | 15000 | Plan
Actual
| Development joint curricula among partnership institution and CEFTER departments | WB | 15000 | 2000 | 5000 | 5500 | 2500 | 15000 | Plan
Actual
| Identification of joint training needs for academic and professional staff in post-harvest science and management | WB | 12000 | 2000 | 3000 | 4500 | 2500 | 12000 | Plan
Actual
| Stakeholders meeting to review progress at ACE | WB | 12000 | 2000 | 3000 | 5000 | 2000 | 12000 | Plan
Actual
| Domestication of curricula in the departments at BSU (Independent review of draft curricula) | WB | 6000 | 1000 | 1500 | 2000 | 1500 | 6000 | Plan
Actual
| Faculty and students training (Staff on PG fellowship) | WB | 20000 | 4000 | 5000 | 7500 | 3500 | 20000 | Plan
Actual
| Mount short courses,workshops and conferences on topics in post-harvest sciences and management (Food Safety and Hygiene) | WB | 15000 | 3500 | 4000 | 4500 | 3000 | 15000 | Plan
Actual
| Institute lecture series: NSPRI organised on Impact of Climate change on PHL | WB | 10000 | 2500 | 2500 | 3000 | 2000 | 10000 | Plan
Actual
| Produce and circulate monographs targeted at awareness creation and extension to rural farmers | WB | 6000 | 1000 | 2000 | 2500 | 500 | 6000 | Plan
Actual
| Support Research fellowships( Sponsor staff of partner institutions on PG programs) | WB | 15000 | 3500 | 3500 | 6000 | 2000 | 15000 | Plan
Actual
| Plan for achieving collaborations with International partners Joint research and Accredition activities (partnership Funding/activities with LJMU) | WB | 35000 | 6000 | 6000 | 15000 | 8000 | 35000 | Plan
Actual
| Start long faculty exchanges between CEFTER, and Universities in Africa | WB | 24000 | 5000 | 6000 | 10000 | 3000 | 24000 | Plan
Actual
| Start of joint research projects between CEFTER,universties and research insttutes elsewhere in Africa | WB | 15000 | 3000 | 3500 | 6000 | 2500 | 15000 | Plan
Actual
Actual
| Produce operational manuals for students | WB | 6000 |  |  | 3000 | 3000 | 6000 | Plan
Actual
| Monitoring and evaluation (Travels, stationaries) | WB | 18000 | 4000 | 4500 | 7000 | 2500 | 18000 | Plan
Actual
| Fund raising activities (Meetings, travels, media) | WB | 10500 | 3000 | 2500 | 4500 | 1500 | 10500 | Plan
Actual
| NgREN Communication Services | WB | 300000 | 60000 | 50000 | 130000 | 60000 | 300000 | Plan
Actual
| Casual staff on Utility services (Cleaners, security) | WB | 40000 | 8000 | 10000 | 14000 | 8000 | 40000 | Plan
Actual
| Provide Automated accounting System | WB | 20000 | 4500 | 6000 | 6500 | 3000 | 20000 | Plan
Actual
|  | TOTAL | 1429000 | 238000 | 275750 | 480500 | 240250 | 1429000
NOTE:
1. operating manuals for students are produced every year.

## Operating Cost
SUB-COMPONENT | ACTIVITIES
Component 1: Strengthening Africa Centers of Excellence
Activity No | ACIVITIES | ESTIMATED BUDGET ($)
Component 1: Strengthening Africa Centers of Excellence
1 | Bi-Weekly meetings of Project Management Committee Members | 2000
2 | Bi-Annual meeting of Industry and Sectoral Advisory Board members | 5000
3 | Annual meeting of International Advisory Board members | 13000
4 | Participate in 2 Regional ACE workshops by Project staff | 60000
5 | Renew/ establish partnership and develop MOU with Partners | 10000
6 | Organise trainings on sexual harrassment, environmental management and safeguard for faculty, staff and students. | 20000
7 | Conduct air and water quality and training on waste management | 3000
8 | Stipends to regional students | 150000
9 | Salaries for project staff | 150000
10 | Administrative Expenses | 100000
11 | Program marketing and 70 Students’ enrolment | 20000
12 | Support participating departments with resources for teaching and external examinations | 40000
13 | Conduct orientation workshops for new students | 10000
14 | Provide student permits for regional students | 10000
15 | Support International research publication with national partners (payment for journal publications) | 30000
16 | Support International research publication with regional/international partners (payment for journal publications) | 15000
17 | Promote and support grant writing by staff and faculty | 20000
18 | Plan and organize merit-based local/regional/international internship placements for 4 staff | 20000
19 | Plan and organize merit-based local/international internship placements for 200 students | 40000
20 | Conduct a needs assessment survey | 2000
21 | Develop curricula with stakeholders | 2000
22 | Review submitted research proposals and use set guidelines to select successful proposals | 500
23 | Develop concept note and agenda for workshops | 1500
24 | Organize quarterly (3) workshops (all hybrid) in 2024 | 15000
25 | Conduct feasibility studies | 3000
26 | Develop a business plan for the incubator | 3000
27 | Support for regional and international conference attendance and manuscript preparation by students and faculty | 50000
28 | Support 4 multidisciplinary team to develop regional research collaborations | 60000
29 | Provide start-up grants for proposed patents for faculty and students | 100000
30 | Update and submit Interim Financial Reports as and when due | 2000
31 | Support biannual Internal auditing and annual external auditting of CERHI account system and annual procurement audit. | 2000
32 | Upload all financial reports to CERHI website for transparency | 2000
33 | Follow approved procurement rules in works, consultancy and supply of goods and services to the centre | 2000
34 | Undertakethe intervention plan activities as approved by the World Bank and AAU | 10000
35 | Conduct meetings with national and regional partners to identify other revenue activities | 20000
993000

## SUMMARY
CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
UNIVERSITY OF BENIN, EDO STATE
SUMMARY
THE EXCHANGED RATE USED IS ₦756 PER US DOLLAR
GOODS
| LOT 2 : LABORATORY EQUIPMENT | 200287.71
| LOT 1 STATIONERY, LECTURE MATERIALS | 65000
| LOT 2 FURNISHING | 100000
| LOT 3 ONLING SUBSCRIPTIONS | 60000
TOTAL |  |  | 225000
WORKS |  |  | 0
| CONSULTANCY SERVICES |  | 60000
OPERATING COST |  |  | 993000
GRAND TOTAL |  |  | 1278000