## CERHI
Name of Center | CENTRE OF EXCELLENCE IN REPRODUCTIVE HEALTH INNOVATION (CERHI)
Institution | UNIVERSITY OF BENIN |  |  | On Schedule
Country | NIGERIA
Center Leader | PROFESSOR FRIDAY OKONOFUA |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2024 - DECEMBER 2024
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Y5Q1 |  |  | 2024 Y5Q2 |  |  | 2024 Y5Q3 |  |  | 2024 Y5Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Develop and support centre governance, structure and strategy \ DLI Action: 1
Sub-Action 1a: Meetingsand Partnerships
Activity 1: Bi-Weekly meetings of Project Management Committee Members | Once in 2 weeks meetings | Nil | [12 empty] | Bi-weekly meetings conducted | Nil | 2000 | 0 | 0 | Program Manager
Activity 2: Bi-Annual meeting of Industry and Sectoral Advisory Board members | Twice a year | All academic, industry and sectoral partners | [12 empty] | Bi-annual meet\ings conducted | Nil | 5000 | 0 | 0 | Project Coordinator
Activity 3: Annual meeting of International Advisory Board members | Once a year | All international academic partners | [12 empty] | Annual meeting conducted | Nil | 13000 | 0 | 0 | Centre Leader
Activity 4: Participate in 2 Regional ACE workshops by Project staff | Twice a year | All centres, experts and AAU and World Bank staff | [12 empty] | Project staff attend 2 ACE regional meetings | Nil | 60000 | 0 | 0 | Program Manager
Activity 5: Renew/ establish partnership and develop MOU with Partners | Continuous activity | All centre partners and new ones | [12 empty] | Patnerships renewed | Nil | 10000 | 0 | 15000 | Deputy Centre Leader
Activity 6: Organise trainings on sexual harrassment, environmental management and safeguard for faculty, staff and students. | Plan to have all the Center's Faculty, Staff and Students to attend training sessions on sexual harrassment, environmental management and safeguard | Nil | [12 empty] | Staff completes training | Nil | 20000 | 0 | 0 | Program Manager
Activity 7: Conduct air and water quality and training on waste management | As contained in the ESMP | Nil | [12 empty] | Staff completes training | Nil | 3000 | 0 | 0 | Program Manager
Sub-Action 1b: Internet and E-books and Journals subscription
Activity 1: Annual Subscription of NgREN | Payment for annual subscription | Nil | [12 empty] | NgREN subscibed | Nil | 30000 | 0 | 0 | Program Manager
Activity 2: Annual subscription of EBSCOHOST | Payment for annual subscription | Nil | [12 empty] | EBSCOHOST subscribed | Nil | 15000 | 0 | 0 | Program Manager
Activity 3: Annual subcription of Science-Direct | Payment for annual subscription | Nil | [12 empty] | Science-Direct subscribed | Nil | 15000 | 0 | 0 | Program Manager
Sub-Action 1c: Administrative Activities
Activity 1: Stipends to regional students | Monthly stipends to 28 regional students (PhD and MSc) to cover feeding and other living expenses | Nil | [12 empty] | Stipends paid | Nil | 150000 | 0 | 0 | Accountant
Activity 2: Salaries for project staff | Monthly salaries for externally hired staff (Program Manager, Assistant Program Manager, Web Master/Communication Officer, M&E Assistants, Corp Members and Janitors) | Nil | [12 empty] | Salaries paid | Nil | 150000 | 0 | 0 | Accountant
Activity 3: Administrative Expenses | Reagents for research laboratory, stationeries, maintenance and repairs of office equipment, CERHI complex, guest house and hostel maintenance and repairs, diesel for generator, fuelling and maintenance of CERHI bus. | Nil | [12 empty] | Smooth running of the project | Nil | 100000 | 0 | 0 | Program Manager
Action 2: Development impact: Support independent evaluation \ DLI Action: 2
Sub-Action 2a: End of project Evaluation
Activity 1: Prepare for visit of independent external evaluators for end of project evaluation | To be determined by the AAU and World Bank | Nil | [12 empty] | To be determined by the AAU and World Bank | Nil | 0 | 0 | 0 | All centre team members
Action 3: Strengthen excellence in educational programmes \DLI Action: 3
Sub-Action 3a: Student enrollment
Activity 1: Program marketing and 70 Students’ enrolment | Place adverts on newspaper, radio gingles, television, website, share leaflets with partners | CERHI national and regional partners | [12 empty] | National and regional students enrolled | Nil | 20000 | 100000 | 0 | Program Manager and M&E Officer
Activity 2: Production of office administrative/academic materials, students’ handbook, Stationeries, Internet Communication, bills, Bank Charges etc. | Printing of students' handbooksand other administrative activities | Nil | [12 empty] | Administrative activities completed | Nil | 20000 | 0 | 0 | Program Manager and M&E Officer
Sub-Action 3b: Student support
Activity 1: Support participating departments with resources for teaching and external examinations | Allowance for services rendered, equipment maintenance etc | nil | [12 empty] | Departments equiped with needed resources | Nil | 40000 | 0 | 5000 | Deputy Centre Leader
Activity 2: Conduct orientation workshops for new students | Centre staff and faculty will provide detailed information about the school and programs | Nil | [12 empty] | Orientation workshop conducted | Nil | 10000 | 0 | 0 | Deputy Centre Leader
Activity 3: Provide student permits for regional students |  | Nil | [12 empty] | Permits given to regional students | Nil | 10000 |  |  | Program Manager
Activity 4: Provide reproductive health textbooks and journals for CERHI library | Annual subscription for reproductive health journals and books | Nil | [12 empty] | CERHI library updated with new textbooks and journals for faculty and students consumption | Nil | 20000 |  |  | CERHI Librarian
Sub-Action 3c: Short courses
Activity 1: Plan and implement 2 short courses in reproductive health in UNIBEN and partner institutions | CERHI and her partners will host short courses for at least 48 hours per short course | CERHI regional partners | [12 empty] | Short courses conducted | Nil | 60000 | 100000 | 15000 | Program Manager and M&E Officer
Action 4: Strengthen teaching and learning excellence \DLI Action: 4
Sub-Action 4a: Publications
Activity 1: Support International research publication with national partners (payment for journal publications) | Joint research publications by faculty, students and partners | National academic and industry partners | [12 empty] | Publications done with national partners | Nil | 30000 | 50000 | 15000 | Centre Leader
Activity 2: Support International research publication with regional/international partners (payment for journal publications) | Joint research publications by faculty, students and partners | Regional/international academic and industry partners | [12 empty] | Publications done with regional and international partners | Nil | 15000 | 50000 | 5000 | Centre Leader
Sub-Action 4b: Improving teaching and lerning methods
Activity 1: Improving faculty teaching methods and faculty development (Equip participating departments with teaching and learning materials) | Purchase of printers, inks, photocopiers, stationeries and general equipment repairs for participating departments | Nil | [12 empty] | Participating departments equipped to face daily work | Nil | 25000 | 0 | 0 | Program Manager
Activity 2: Provide training on simulation program by Harvard team (technical support) and shipping of simulation equipment | Staff and students will be trained on the use of the simulation equipment | Nil | [12 empty] | project sustained | Nil | 50000 | 0 | 0 | Centre Leader
Activity 3: Purchase of reagents and repairs of equipment in the molecular laboratory | All equipment are in good use | Nil | [12 empty] | project sustained | Nil | 50000 | 0 | 0 | Lab Scientist
Action 5: Enhancing relevance of Education & Research \DLI Action: 5
Sub-Action 5a: Revenue generation
Activity 1: Promote and support grant writing by staff and faculty | Grant officer to identify available grants and inform faculty and students | Nil | [12 empty] | Grants received by CERHI | Nil | 20000 | 0 | 0 | Program Manager
Activity 2: Improve CERHI's internal revenue generation by implementing activities in the business plan | The business plan of CERHI implemented | Industry partners | [12 empty] | project sustained | Nil | 0 | 0 | 0 | Program Manager
Sub-Action 5b: Internships
Activity 1: Plan and organize merit-based local/regional/international internship placements for 4 staff | Identify industries and send staff for atleast 1 month internship | Industry partners | [12 empty] | Staff completes internship | Nil | 20000 | 50000 | 0 | Program Manager
Activity 2: Plan and organize merit-based local/international internship placements for 200 students | Identify industries and send students for atleast 1 month internship | Industry partners | [12 empty] | Students completes internship | Nil | 40000 | 70000 | 0 | Program Manager
Sub-Action 5c: Enterpreneurship and Innovation
Activity 1a: Conduct a needs assessment survey | Needs assessment survey is required to ascertain the needs and skills to be used in developing the postgraduate curricula | Nil | [12 empty] | Needs assessment done | Nil | 2000 |  |  | Committee Chairperson
Activity 1b: Identify and engage stakeholders/faculty | Stakeholders and faculty to teach or train students must be identified | Nil | [12 empty] | Stakeholders engaged | Nil | 0 |  |  | Committee Chairperson
Activity 1c: Develop curricula with stakeholders | As required by the module, an enriched innovative and entrepreneurship curriculum will be developed | Nil | [12 empty] | Curricula developed | Nil | 2000 |  |  | Dean of PG School and Committee
Activity 1d: Submit report of needs assessment and draft curricula to CERHI | CERHI project team will review all reports to ensure that they align with the goal of the centre | Nil | [13 empty] | Nil | 0 |  |  | Dean of PG School and Committee
Activity 1e: CERHI team will conduct independent review of the curricula | CERHI project team will review all reports to ensure that they align with the goal of the centre | Nil | [13 empty] | Nil | 0 |  |  | CERHI PMC
Activity 1f: Approve curricula for implementation starting from 2022/2023 session | The revised curricula must be approved by the university management before it can be part of the post graduate program at CERHI | Nil | [13 empty] | Nil | 0 |  |  | Dean of PG School and Vice Chancellor
Activity 1g: Train faculty and students using curricula | All CERHI students will undergo atleast one course in entrepreneurship before graduation | Nil | [12 empty] | Faculty trained | Nil | 0 |  |  | PG Coordinators and Heads of Department
Activity 2: Revise CERHI research proposal template to contain ‘impact of the research’ | CERHI already has a research proposal template, but there is need to improve the template to contain activities about impact and sustainability. | Nil | [13 empty] | Nil | 0 |  |  | Committee Chairperson
Activity 3: Review submitted research proposals and use set guidelines to select successful proposals | Using set guidelines, the committee will revise submitted proposals and streamline them to the best 3 that will be funded | Nil | [13 empty] | Nil | 500 |  |  | Committee Chairperson
Activity 4: Monitor on-going research | The committee will also monitor the research supported with the seed grants | Nil | [13 empty] | Nil | 0 |  |  | Fund Management Committee
Activity 5: Set-up a capacity building workshop organizing committee | Athere is need to have a committee to coordinate the workshops | Nil | [13 empty] | Nil | 0 |  |  | CERHI, Program Manager, Research Coordinator
Activity 6: Develop concept note and agenda for workshops | The concept note will guide the proposed workshops | Nil | [13 empty] | Nil | 1500 |  |  | Committee Chairperson
Activity 7: Identification of resource persons to teach during the workshops | Qualified resource persons to teach during the workshops is required | Nil | [13 empty] | Nil | 0 |  |  | Committee Chairperson
Activity 8: Organize quarterly (3) workshops (all hybrid) in 2022 | The university staff and students require more knowledge on technology transfer and commercialization to guide their research | Nil | [13 empty] | Nil | 15000 |  |  | Committee Chairperson
Activity 9: Constitute a sector-focused incubator team that will do the following; | There is need to have a team to coordinate the module | Nil | [13 empty] | Nil | 0 |  |  | Vice Chancellor /CERHI Project Management team
Activity 9a: Conduct feasibility studies | There is need to conduct feasibilty studies to understand what is available and what to plan for | Nil | [13 empty] | Nil | 3000 |  |  | Team leader
Activity 9b: identify stakeholders | Collaborative stakeholders are required for the module to be successful | Nil | [13 empty] | Nil | 0 |  |  | Team leader
Activity 9c: develop a business plan for the incubator, | The team will develop a business plan that will guide the sustainable activities of the incubator | Nil | [13 empty] | Nil | 3000 |  |  | Team leader
Activity 9d: The centre team will review the plan | The business plan will be reviewed and finalized | Nil | [13 empty] | Nil | 0 |  |  | Team leader
Activity 9e: Approval and implementation of the plan | The business plan will be approved by management and the university will take it as a guide for their future incubator set-up | Nil | [13 empty] | Nil | 0 | 0 | 0 | Team leader
Activity 10: Support for regional and international conference attendance and manuscript preparation by students and faculty | As and when due | Academic and Industry partners | [12 empty] | Conferences attended | Nil | 50000 | 0 | 0 | Program Manager
Activity 11: Support 4 multidisciplinary team to develop regional research collaborations | Proposal presentations and team selections will be carried out | Academic and Industry partners | [12 empty] | Multidisciplinary teams identified and equipped | Nil | 60000 | 20000 | 0 | Deputy Centre Leader
Activity 12: Provide start-up grants for proposed patents for faculty and students | Grants given to 5 groups/individuals for patenting or commercialization | Academic and Industry partners | [12 empty] | teams or individuals provided with grants | Nil | 100000 | 20000 | 0 | Deputy Centre Leader
Action 6: Fiduciary Enhancement \DLI Action: 6
Sub-Action 6a: Fiduciary Enhancement
Activity 1: Update and submit Interim Financial Reports as and when due | Reporting | Nil | [12 empty] | Timely report submitted | Nil | 2000 | 15000 | 0 | Accountant
Activity 2: Support biannual Internal auditing and annual external auditting of CERHI account system and annual procurement audit. | Auditing | Nil | [12 empty] | Audit review conducted | Nil | 2000 | 15000 | 0 | Accountant and Procurement Officer
Activity 3: Upload all financial reports to CERHI website for transparency | Web links | Nil | [12 empty] | Web links sent to World Bank for confirmation | Nil | 2000 | 15000 | 0 | Accountant
Activity 4: Follow approved procurement rules in works, consultancy and supply of goods and services to the centre | Annual Procurement plans | Nil | [12 empty] | Procurement plans completed | Nil | 2000 | 15000 | 0 | Procurement Officer
Action 7: Institutional Impact \DLI Action: 7
Sub-Action 7c: PASET Regional Benchmarking
Activity 2: Undertakethe intervention plan activities as approved by the World Bank and AAU | Guidelines for the benchmarking activities will be used | Nil | [12 empty] | Benchmarking score passed | Nil | 10000 | 0 | 0 | UNIBEN team
Action 8: Sustainability Activities
Activity 1: Set up a committee to develop a proposal for the establishment of the endowment fund | A committee will develop the proposal which will serve as a guide | Nil | [12 empty] | Committee conducted | Nil | 0 |  |  | Vice Chancellor/ Centre Leader
Activity 2: Conduct meetings with national and regional partners to identify other revenue activities | Online and physical meetings with partners for partners to contribute funds | Nil | [13 empty] | Nil | 20000 | 2000000 | 1000000 | Vice Chancellor/ Centre Leader
Activity 3: Set up a fund management board | The committee will form the fund management board to guide and monitor funds that were received and how its being used. | Nil | [13 empty] | Nil | 0 |  |  | Vice Chancellor/ Centre Leader
[15 empty] | GRAND TOTAL |  | 1278000 | 2520000 | 1055000
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus